## 000-F-ITP-60001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 3 | Ahmed Bucheeri | To provide WPS & PQR for reviewing
2 | Text Box | Page 3 | Ahmed Bucheeri | It shall be 100%
3 | Text Box | Page 3 | Ahmed Bucheeri | Before & after PWHT
4 | Text Box | Page 6 | Ahmed Bucheeri | PMI to be carried out for Alloyed materials
5 | Text Box | Page 7 | Ahmed Bucheeri | Percentage of testing can reach 100% basis welding process
6 | Text Box | Page 7 | Ahmed Bucheeri | To provide WPS & PQR for reviewing
7 | Text Box | Page 7 | Ahmed Bucheeri | PMI
8 | Text Box | Page 8 | Ahmed Bucheeri | To provide WPS & PQR for reviewing