## 000-K-GRD-60002-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 18 | Ahmed Habib | Laptop shall be fully configured with the necessary application software and configuration required and with all necessary accessories and software suitable for performing engineering and maintenance funtions when connected to the system. Refer to BMPS-J01. That shall be reflect on MOC, SOC & ROC.
2 | Text Box | 1 | Hasan Asad | The Contractor/Supplier/Vendor shall provide a complete LCCA report for 20 years considering the main equipments and components. The LCCA shall serve the procurement decision and maintenance strategy and spare parts selection.
3 | Text Box | 4 | Hasan Asad | The Contractor/Supplier to verify if air ejector or steam ejector to be used.
4 | Text Box | 4 | Hasan Asad | 3 Axial probes shall be provided.
5 | Text Box | 4 | Hasan Asad | Turbine shall be equipped with mechanical trip mechanism.
6 | Text Box | 6 | Hasan Asad | Accumulator charging kit to be provided part of the package.
7 | Text Box | 7 | Hasan Asad | The Contractor/Supplier shall study the layout for the possibility of storing the compressor bundle cradle at the platform, if possible.
8 | Text Box | 18 | Hasan Asad | Rotor metal container shall be pressurized to protect the rotor preservation.
9 | Text Box | 19 | Hasan Asad | Supplier/Vendor Training: A detailed training shall be provided to Owner Operation and Maintenance that includes Operation, Maintenance and troubleshooting.
10 | Text Box | 1 | Isamu | Please indicate here the tag number of each compressor and ST driver, service description, unit name, unit description, etc. for immediate reference in typical cover page
11 | Text Box | 3 | Isamu | Document priority issue is no longer applicable as it is negated by BMPS-K2 section II & BMPS-A2 section 5.3. and parag 5.1 of this doc. Please delete and rewrite
12 | Callout | 5 | Isamu | Seal Gas Booster unit is not specified on any data sheet of the compressors in this MR including those with high settling pressure and steam turbine driven machines. Please make clear booster unit requirements on respective comp data sheets
13 | Callout | 6 | Isamu | with flange and blind and tagged (Normally closed)
14 | Text Box | 1 | Omran A | All comments which starts with a prefix "**" & they are related to systems (Hardware/Software) & Instrumentations shall be reflected at ROC, MOC & SOC***
15 | Text Box | 5 | Omran A | **General Statement for obsolescence Any Hardware/Software shall continue to be supported for more than 10 years. OEM shall confirm that the designed system components will not become obsolete within the next 5 years from the date of supply & that any subsequent revisions to the software provided will be backwards compatible. In the belief that portions of the system will be eventually withdrawn from sale, a firm commitment is required from the OEM that there will be repair capability or equivalent parts and/or products available for a minimum of ten years from the withdrawal date.
16 | Text Box | 5 | Omran A | **Control cabinet shall have Local HMI screen with graphical representation (monitoring and controlling with different security level/privilege). Local HMI shall have the same functionality of remote HMI/SCADA). This shall be reflected on ROC, MOC and SOC
17 | Text Box | 7 | Omran A | **d) Control Systems commissioning spares to be included.
18 | Text Box | 7 | Omran A | **Method statement and Risk Assessment shall be prepared by vendor prior to SAT for the three operating centres.
19 | Text Box | 7 | Omran A | **Comprehensive training for Engineers "Automation, Instrumentations" to be provided.
20 | Text Box | 8 | Omran A | **Control Systems namely (DCS, SCADA, etc...)
21 | Text Box | 8 | Omran A | **&Instruments Engineers
22 | Text Box | 8 | Omran A | **Systems Architecture & Control Narrative
23 | Text Box | 8 | Omran A | **Automation &Instruments Engineers
24 | Text Box | 8 | Omran A | **Automation &Instruments Engineers
25 | Text Box | 8 | Omran A | **& Instruments Engineers
26 | Text Box | 8 | Omran A | **Automation &Instruments Engineers
27 | Text Box | 8 | Omran A | **& IFAT
28 | Text Box | 8 | Omran A | **& CHAZOP
29 | Text Box | 8 | Omran A | **/IFAT
30 | Text Box | 8 | Omran A | **Automation &Instruments Engineers
31 | Text Box | 8 | Omran A | **Bapco Rep &
32 | Text Box | 13 | Omran A | **Control systems will be connected to GPS Clock. Time-synchronizing facility shall not result in degrading system performance or data transfer rate. Also, It shall not affect any calculation, PID Blocks/Controllers, as per BMPS-J13_0
33 | Text Box | 16 | Omran A | **Control Systems Hardware & their Application Software shall also be included
34 | Text Box | 16 | Omran A | **Control Systems layouts and system architectures drawings shall be supplied
35 | Text Box | 17 | Omran A | ** Comply with BMPS-S12 " Guidance for preparations of spare parts"
36 | Text Box | 18 | Omran A | **all application software shall be loaded with perpetual license
37 | Text Box | 3 | Rashed Almudahka | Terminology should be identified in general outline section, e.g. CONTRACTOR, SUPPLIER, COMPANY, PURCHASER TTSJV to clarify these terminologies with their definitions
38 | Call-out | 18 | Rashed Almudahka | Capital spares shall be in compliance with FEED ITP, volume 2, section 6.5, attachment-1.