## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ |  | A.Jabbar Mahmood | Typo in the title: NAPHTHA | Noted. It will be implemented in revision A | Y
2 | Callout |  | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | Y
3 | Call-out |  | 986131 | Repeat the clouded section on all pages of the drawing. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | Y
4 | Callout |  | alexis.martinez | Add the note "Column will be subjected to steam-out operation. Additional design conditions shall be -10 psig at 300 °F" | Already included in first page | N
5 | Call-out |  | bapco-user | Note 17: Change to "ASTM A193 for the bolts and ASTM A194 for the nutes". | Noted. It will be implemented in revision A | Y
6 | Callout |  | alexis.martinez | The Nozzle N22 (Minimum Flow) is not shown in the column general arrangement drawing. Show the nozzle N22. | Noted. It will be implemented in revision A | Y
7 | Call-out |  | Ahmed Marhoon | According to the PID, N22 (Pumps Min Flow) could be close to the level bridle nozzles. Designer shall ensure that the minimum flow return is located such that it does not create disturbances to the level measurement. | Noted | Y
8 | Cloud+ |  | Ahmed Marhoon | Direction to North, is it applicable for this drawing? If applicable, is it shown at the right direction? Otherwise, delete from the drawing. Typical for similar drawing. | Orientations are on hold. However north indicates always 0º | N
9 | Cloud+ |  | Ahmed Marhoon | HP/LP level nozzles elevations need to be reviewed in view of the final operating range. Current revision shows the Nozzle elevations and the operating range (HLL & LLL) exactly the same which could create limitation/saturation in the rangeability/span of the level transmitters during operation in Max and Min levels. This is Typical comment for similar configurations. | This is a preliminar sketch. These nozzles will be relocated by instrumentation department in a later stage | N
10 | Call-out |  | 986131 | Review the need to have two nozzles (N5A and N5B) for the parallel have independent reboiler circuit. This is also communicated owner P&ID comment no 66 (excel). | Note 7 in P&ID BRA-227060 Sheet 29 asks for symmetrical distribution for both tube and shell sides. Independent column outlet nozzles are not required. | Y
11 | Call-out |  | 986131 | Review the need to have two nozzles (N7A and N7B) for the parallel have independent reboiler circuit. This is also communicated owner P&ID comment no 66 (excel). | Note 7 in P&ID BRA-227060 Sheet 29 asks for Symmetrical distribution for tube and shell sides. Independent reboiler return nozzles are not required. | Y
12 | Call-out |  | 986131 | Review the seal pan and Reboiler outlet arrangement based on the reboiler design (once through or circulating). The current arrangement is prone to liquid entrainment and foaming. | Reboiler configuration is once through. Refer to bottom arrangement details on Process data sheet 010-C-DAT-10005-001. | Y
13 | Text Box |  | 986131 | Based on owner clarification on the item 7 of Kick off meeting (LN TVP) the hydraulics of the column to be rechecked. Based on the revised hydraulics review the nozzle/internals size. | Column sizing is pending on the evaluation of this requirement.