## 011-A-EQL-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | 986131 | Correct name to - LVGO PA AIR COOLER FINFAN
2 | Call-out | 3 | 986131 | Consider renaming as - LVGO PA AIR COOLER
3 | Cloud+ | 4 | 986131 | Correct name to - LVGO PA AIR COOLER FINFAN
4 | Cloud+ | 5 | 986131 | Correct name to - LVGO PA AIR COOLER ELECTRIC MOTOR
5 | Cloud+ | 6 | 986131 | Correct name to - LVGO PA AIR COOLER ELECTRIC MOTOR
6 | Text Box | 1 | Ahmed Ali | Ensure that all equipment i.e. exchangers, pumps are properly design for 7VDU by-pass case.
7 | Call-out | 3 | Ahmed Ali | MVGO recycle line to be considered in the Column design and data sheet
8 | Call-out | 5 | Ahmed Ali | ensure the MVGO pumps data sheet updated for the new MVGO recycle stream
9 | Text Box | 1 | MAK | General Comment: Use the latest document template issued to TTSJV as part of the Homogenization Procedure. The cover page shall be orientated the same as the documents they apply to.
10 | Call-out | 3 | MAK | 011E0001D/E/F are missing. Any reason?
11 | Call-out | 7 | MAK | Change to 011OMG0001
12 | Texto escrito a mÃ¡quina | 1 | moreno | 2018-08-01
13 | Call-out | 1 | Raj | The Item Index has mainly been reviewed for the Equipment Numbering. Many design parameters cannot be checked as preceding engineering documents such as equipment datasheets, MSD etc has not been submitted/completed
14 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco.