## 018-A-PFD-00001-009-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud |  | Fatema Hashem
2 | Cloud |  | Fatema Hashem
3 | Callout |  | Fatema Hashem | ADD THE SOURCE OF KEROSENE AND DIESEL CUTTERSTOCKS
4 | Highlight |  | Fatema Hashem
5 | Callout |  | Fatema Hashem | "DIESEL PRODUCT"
6 | Highlight |  | Fatema Hashem
7 | Highlight |  | Fatema Hashem
8 | Callout |  | Fatema Hashem | COMPLETE THE SIGNAL TAG. "FROM LC5007A/B"
9 | Highlight |  | Fatema Hashem
10 | Cloud |  | Fatema Hashem
11 | Callout |  | Fatema Hashem | LINE 406 TERTIARY THICKNESS
12 | Cloud |  | Fatema Hashem
13 | Callout |  | Fatema Hashem | CHANGE THE FEED LINE 450 ENTRY TO THE STRIPPER SUCH THAT THE LINE ENTERS ON THE LEFT SIDE. MOVE THE STRIPPER UP TO MINIMISE LINE CROSSINGS
14 | Cloud |  | Fatema Hashem
15 | Callout |  | Fatema Hashem | CORRECT THE DRAWING TO BE A TRUE REPRESENTATION OF THE VACUUM COLUMN. THE COLUMN IS NOT HAVE A SMALLER DIAMETER AT THE TOP
16 | Arrow |  | Fatema Hashem
17 | Arrow |  | Fatema Hashem
18 | Arrow |  | Fatema Hashem
19 | Arrow |  | Fatema Hashem
20 | Arrow |  | Fatema Hashem
21 | Circle |  | Fatema Hashem | N
22 | Arrow |  | Fatema Hashem
23 | Arrow |  | Fatema Hashem
24 | Cloud |  | Fatema Hashem
25 | Callout |  | Fatema Hashem | SIMPLIFY THE VAC COLUMN BOTTOM CIRCUIT BY REARRANGING THE LINES AS SHOWN TO MINIMISE LINE CROSSINGS. AVOID BREAKING THE MAIN FEED LINE.