## 018-F-DAT-00003-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Unchecked | Ahmed Bucheeri | Provide basis of selecting SS304
2 | Call-out | Unchecked | Ahmed Bucheeri | Provide basis of selecting SS304
3 | Call-out | Unchecked | Ahmed Bucheeri | Provide basis of selecting SS304
4 | Callout | Unchecked | Fatema Hashem | and to include flow pass control valves
5 | Call-out | Unchecked | Mahdi Ali | Do not use FEED drawing number
6 | Callout | Unchecked | Fatema Hashem | ADD NOTE TO THE DATASHEET: "Vendor to propose the coil arrangement in the radiant section that will ensure that the maximum allowable film temperature shall not be exceeded in each single tube. Vendor to specify whether the coils enter the radiant section from the top or the bottom and justify their proposal"
7 | Callout | Unchecked | Fatema Hashem | ADD NOTE TO THE DATASHEET: "Vendor to advise the oil velocity at the inlet to the radiant section"
8 | Text Box | Unchecked | Hasan Asad | Isolation Guillotone shall ensure zero leakage if possible (i.e. recommending double seat arrangement). Others details such as manual gear operation vs. hydraulic/electric motor, double sealing arrangement and seal life expectancy and other details should be discussed during the detailed design and such information should be captured in the Maintenance Consideration report.