## 018-G-DAT-00003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Please follow same comments made on Train 1 & 2 pumps
2 | Call-out | 2 | Rashed Almudahka | ADD Note 11
3 | Call-out | 2 | Rashed Almudahka | ADD Note 14
4 | Call-out | 3 | Rashed Almudahka | indicate "yes" as per FEED data sheet
5 | Call-out | 3 | Ravi Kumar | Confirm LXG31H piping spec can cater to the discharge circuit design pressure of 3775 psig else develop suitable piping spec
6 | Callout | 4 | Fatema Hashem | ADVISE WHY THE SEAL FLUSH PIPING PLAN ON 1RHCU QUENCH OIL PUMP DATASHEET HAS BEEN DELETED. FILL AS PER FEED/LICENSOR DATASHEET
7 | Call-out | 5 | Rashed Almudahka | Inconsistency from FEED document. Please clarify
8 | Call-out | 5 | Rashed Almudahka | As per FEED data sheet, operation to trip speed is required. please clarify
9 | Text Box | 7 | Rashed Almudahka | Please refer to the comments made on the notes in DAT-00002-001, as they are applicable here as well