## 018-K-DAT-00002-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fatema Hashem | GENERAL COMMENT: PLEASE REFER TO BMPS-A8 SECTION 4.5.1: DO NOT INDICATE FIGURES IN EUROPEAN STYLE (WHICH USES COMMAS FOR DECIMAL POINTS AND PERIODS FOR THOUSANDS SEPARATORS), USE UK/US STYLE WITH PERIODS FOR DECIMAL PLACES AND COMMAS FOR THOUSANDS SEPARATORS. CHECK AND CORRECT ALL FIGURES
2 | Callout | 2 | Fatema Hashem | ADVISE THE REASON FOR REMOVING DIFFERENTIAL PRESSURE
3 | Callout | 2 | Fatema Hashem | ENSURE THAT THE DATASHEET IS CONSISTENT WITH THE H&MB AND REFLECTS THE LATEST DATA
4 | Callout | 4 | Fatema Hashem | ENSURE THAT THE DATASHEET IS CONSISTENT WITH THE H&MB AND REFLECTS THE LATEST DATA
5 | Text Box | 1 | Hasan Asad | The below points are applicable for 018K0002A/B, 021K0001, 023K0002A/B, 051K0001A/B: 1. 3 Axial probes shall be provided as per BMPS-A3, section 8.5.1. 2. The seal system shall be designed for process depressuring operation. 3. The seal system shall be capable of withstanding the maximum pressure that can occur after a compressor trip. 4. The seal system primary gas buffer takeoff shall be designed to eliminate any liquid carry-over. 5. The seal system shall provide seal leakage rate for each operating condition. 6. The dry gas seals vendor shall indicate the maximum expected life of the seal elastomer and the maximum shelf life of elastomer for the spare seals. 7. Complete unit test shall be performed (if required, case-by-case to be verified). 8. SAT for anti-surge control CCC system functionality to be performed. 9. Mechanical overspeed trip test to be verified on-site together with electronic trip. 10. Lube/Control oil functionality to be verified on-site (SAT). 11. Spare compressor rotor shall be stored in pressurized metal canister and shall be tested during FAT. 12. Maintenance manual shall include detail maintenance strategy and major overhaul instruction. 13. Manual turning device for alignment shall be provided by Vendor/Supplier. 14. The Vendor/Supplier shall provide complete LCCA report for 20 years.
6 | Call-out | 1 | Mahdi Ali | Remove space between equipment number and suffix
7 | Call-out | 11 | Mahdi Ali | Remove space between equipment number and suffix
8 | Call-out | 2 | Rashed Almudahka | identify the changes in the process controls and clarify the reason
9 | Call-out | 7 | Rashed Almudahka | for settling pressure, add a note to identify the responsible party of providing the value.
10 | Call-out | 8 | Rashed Almudahka | Monitor shall be supplied by compressor vendor as per FEED datasheet. please clarify
11 | Call-out | 9 | Rashed Almudahka | mark SUPPLIER icon for anti-surge system as per note 16
12 | Call-out | 10 | Rashed Almudahka | impeller over-speed test shall be (WIT) as per FEED data sheet. please clarify
13 | Call-out | 11 | Rashed Almudahka | please clarify the reason behind deleting note-15. as nowhere in the data sheet is mentioned about the hazardous area classification