## 019-C-GAD-00008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number
3 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018.
4 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT
5 | Cloud+ | 1 | A.Jabbar Mahmood | The design pressure per FEED D/S and Licensor D/S is 2340 psig. CLG to be consulted on the revised design pressure.
6 | Text Box | 1 | A.Jabbar Mahmood | CLG's detailed mechanical drawing with the "Fabrication notes" in RD-140639 shall be included when the vendor is selected,
7 | Cloud+ | 1 | Jawad Alawi | Confirm material type and Swap material spec for shell and heads
8 | Call-out | 1 | Sameer Foujdar | Operating Pressure as per FEED data sheet is 2227 psig to be confirmed.
9 | Text Box | 1 | A.Jabbar Mahmood | This drawing shall be reviewed and approved by the Licensor
10 | Cloud+ | 1 | bapco-user | Is the vessel exposed to high H2S during start up (catalyst sulfiding). This to be checked with licensor and if required add a note.
11 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number
12 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
13 | Callout | 2 | Mohamed Ayyash | Allign
14 | Call-out | 2 | Sameer Foujdar | It is separator not reactor
15 | Cloud+ | 2 | bapco-user | Note 18: Do not match with the CA in table "DESIGN DATA" in page 1 of 3
16 | Callout | 2 | bapco-user | Add: High-Alloy Clad Pressure Vessels - PVM-SU-1322
17 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment.
18 | Text Box | 3 | Mahdi Ali | This shall be sheet 1 of 3
19 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3.
20 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number
21 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note.