## 019-G-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | Shall be changed to 019P0003A/B according to the new equipment numbering
2 | Text Box | 1 | Mahdi Ali | Unit number shall always be 3 digits
3 | Text Box | 1 | Mahdi Ali | Check number!
4 | Text Box | 1 | Mahdi Ali | Equipment code for motors is 'M'
5 | Callout | 1 | Mohamed Ayyash | NO. (Typo) correct on all pages
6 | Callout | 1 | Mohamed Ayyash | Should read 1/9 ( correct all pages)
7 | Text Box | 1 | A.Jabbar Mahmood | The pump head needs to be check considering the UCO viscosity correction made at the end of the FEED (refer to WP2 SOW document)
8 | Text Box | 1 | A.Jabbar Mahmood | General to all pumps: Owner has not received the hydraulic calculations and hence cannot verify the revised pump head and design conditions.
9 | Call-out | 2 | A.Jabbar Mahmood | NPSHa is estimated by CLG as 467 ft (from top of foundation). Check and confirm
10 | Call-out | 2 | A.Jabbar Mahmood | Min CW return pressure at unit battery limit is 36 psig per BMPS A1. Check and confirm
11 | Call-out | 2 | A.Jabbar Mahmood | Min CW inlet pressure at unit battery limit is 65 psig as per BMPS A1. Verify and confirm
12 | Text Box | 3 | Hasan Asad | 7in (180cm) to be verified by Vendor
13 | Callout | 4 | Isamu | TTSJV to add a remark "Vendor to consult seal vendor to employ plan 53B (with bladder) to avoid bubble formation by the pressurizing gas inside the seal pot"
14 | Cloud+ | 4 | Adnan Alothman | Mounting of Seal S. to be checked and verified according to the standard
15 | Text Box | 5 | Hasan Asad | WIT
16 | Text Box | 5 | Hasan Asad | Yes
17 | Call-out | 7 | A.Jabbar Mahmood | Correct the noted NPSHa (449.7 ft is reported in the table above)
18 | Call-out | 7 | A.Jabbar Mahmood | What is the basis for the indicated max CW flow per pump?
19 | Call-out | 7 | A.Jabbar Mahmood | Note 12: The Flash point of UCO is expected to be much higher (higher than 392 F). Check and Confirm
20 | Call-out | 7 | A.Jabbar Mahmood | A note shall be added indicating the warm-up medium (UCO), providing the main properties of UCO.
21 | Call-out | 7 | A.Jabbar Mahmood | Add to Note 24 "..and the warm up line isolation valve is left open by mistake"
22 | Call-out | 7 | A.Jabbar Mahmood | Add to Note 24 "..and the warm-up oil flowrate and temperature".
23 | Cloud+ | 7 | A.Jabbar Mahmood | Correct the P&ID no. to 2520-c019-PID-0021-013-01
24 | Text Box | 7 | A.Jabbar Mahmood | A note to be added stating that the pump head may change as detailed design is developed.
25 | Cloud+ | 7 | bapco-user | 000-G-ITP-70001-001
26 | Callout | 7 | Isamu | Second page shows Normal flow rate. Please indicate rated flow rate if it means 115% of normal. The use of the world design shall be by Vendor only as per API 610 guidance
27 | Callout | 7 | Isamu | TTSJV shall indicate the maximum viscosity and specific gravity to count for motor sizing
28 | Call-out | 7 | Sameer Foujdar | Vendor to Specify the Operation of the the bypass lines on the spill-back valve and suction MOV
29 | Text Box | 8 | Sankara | Indicate the right ambient temperature figures in deg C
30 | Text Box | 8 | Sankara | Delete Ex-p ( Typical)
31 | Text Box | 8 | Mahdi Ali | Equipment code for motors is 'M'
32 | Text Box | 8 | Mahdi Ali | Equipment code for motors is 'M'
33 | Callout | 9 | Mohamed Ayyash | space