## 019-G-DAT-00003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | Shall be changed to 019P0021A/B according to the new equipment numbering
2 | Call-out | 1 | MAK | 019P0021A/B
3 | Text Box | 1 | Mahdi Ali | Unit number shall always be 3 digits
4 | Text Box | 1 | Mahdi Ali | Equipment code for motors is 'M'
5 | Callout | 1 | Mohamed Ayyash | NO. (Typo) correct on all pages
6 | Callout | 1 | Mohamed Ayyash | Should read 1/9 ( correct all pages)
7 | Text Box | 1 | A.Jabbar Mahmood | General to all pumps: Owner has not received the hydraulic calculations and hence cannot verify the revised pump head and design conditions.
8 | Call-out | 2 | A.Jabbar Mahmood | The discharge pressure as in the FEED D/S is 2359 psig. We understand that the pressures have generally increased in the HP circuit. Check and verify.
9 | Call-out | 2 | A.Jabbar Mahmood | Min CW return pressure at unit battery limit is 36 psig per BMPS A1. Check and confirm
10 | Call-out | 2 | A.Jabbar Mahmood | Min CW inlet pressure at unit battery limit is 65 psig as per BMPS A1. Verify and confirm
11 | Text Box | 3 | Hasan Asad | 7in (180cm) to be verified by Vendor
12 | Callout | 4 | Isamu | TTSJV shall specify liquid properties to enable pump manufacturer to select proper seal and seal flush mechanism such as :- -Solid particles content and size. -Toxic service -Leakage allowed ?
13 | Cloud+ | 4 | Adnan Alothman | Mounting of Seal S. to be checked and verified according to the standard
14 | Text Box | 5 | Hasan Asad | WIT
15 | Text Box | 5 | Hasan Asad | Yes
16 | Text Box | 7 | A.Jabbar Mahmood | A note to be added stating that the pump head may change as detailed design is developed.
17 | Cloud+ | 7 | A.Jabbar Mahmood | Amine is classified as "Non-flammable". Check the applicability of the reported flash point and autoignition.
18 | Call-out | 7 | A.Jabbar Mahmood | What is the basis for the indicated max CW flow per pump?
19 | Cloud+ | 7 | bapco-user | 000-G-ITP-70001-001
20 | Callout | 7 | Isamu | Second page shows Normal flow rate. Please indicate rated flow rate if it means 115% of normal. The use of the world design shall be by Vendor only as per API 610 guidance
21 | Call-out | 7 | A.Jabbar Mahmood | 110%
22 | Text Box | 8 | Sankara | Delete Ex-p ( Typical)
23 | Text Box | 8 | Sankara | Indicate the right tempereature figures in deg C
24 | Text Box | 8 | Mahdi Ali | Equipment code for motors is 'M'
25 | Callout | 9 | Mohamed Ayyash | space