## 019-G-DAT-00008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Casella di testo | 1 | LPetroni | 2018-04-20
2 | Callout | 1 | Isamu | Please follow and apply the same comments made on 019-G-DAT-00007-001-RAP where releavant
3 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets.
4 | Callout | 1 | Mohamed Ayyash | Add unit name 2HCU
5 | Text Box | 1 | A.Jabbar Mahmood | General: Decimal points shall be instead of commas as decimal separators
6 | Text Box | 1 | A.Jabbar Mahmood | Owner has not recieved the revised hydrualic calculations and there cannot verify the updated pump suction and discharge pressures.
7 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate.
8 | Callout | 2 | Mohamed Ayyash | Should read 2/12. Correct all pages
9 | Cloud+ | 2 | A.Jabbar Mahmood | The NPSHa was estimated by CLG as 57 ft. Check and confirm
10 | Cloud+ | 2 | A.Jabbar Mahmood | Ensure compliance with BMPS A1. Assumed pressure drop from/to unit B.L will need to be verify during detailed engineering
11 | Callout | 4 | Adnan Alothman | Mounting of Seal Support System on Baseplate to be checked against relative standard and confirm.
12 | Text Box | 7 | Sankara | HV motors in Zone 2 areas shall be Ex-d or Ex-e type only. Refer Query T107: Typical comment
13 | Call-out | 7 | Sameer Foujdar | There is only one pump 19P0006A hence we require only one motor other pump 190006B is turbine driven.
14 | Callout | 10 | Mohamed Ayyash | complete Sheet bottom line
15 | Callout | 12 | Isamu | Delete. NPSHR test already specified as witness
16 | Cloud+ | 12 | A.Jabbar Mahmood | max 60# steam header pressure is 70 psig as per BMPS A1.The exhaust pressure needs to be confirmed considering the line pressure drop.
17 | Text Box | 12 | A.Jabbar Mahmood | Notes 8 and 9 of the FEED D/S shall be included. Spillback requirement shall be confirmed by the pump vendor
18 | Call-out | 12 | Sameer Foujdar | 550 psig steam operating pressure to be as per BMPS A1. This needs to be confirmed 510/540/550 psig.
19 | Call-out | 12 | Mahdi Ali | Use Bapco number. FEED number shall not be used.