## CRS
No. | Rev. | Page No. | author | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | Callout | 2 | Syed Ahmed | Note 13 mentioned 100 psig | Process design pressure is 50 psig. Note 13 is for mechnical requirement. | y | y |  | Syed Ahmed
2 | Callout | 2 | Syed Ahmed | No space | Noted. Will be revised. | y | y |  | Syed Ahmed
3 | Callout | 2 | Saeed Taher | Material and ASTM specifications to be specified for all components. | Noted. Will be add "ASTM". Material for each components is defined by vendor. | y | y |  | Saeed Taher
4 | Callout | 3 | Syed Ahmed | please specify the type like "A stainless steel" | To be specified after receiving vendor information. | y |  |  | Syed Ahmed
5 | Callout | 3 | Syed Ahmed | Start up | Start-up' is not matched for this note. | y |  |  | Syed Ahmed
6 | Callout | 3 | Syed Ahmed | (guard or screen) to be provided to the bottom part of the Thermal Reactor and Burner | To be checked during vendor clarification. | y |  |  | Syed Ahmed
7 | Callout | 4 | Syed Ahmed | please add additional two notes : *Vendor shall specify Refractory Expansion Joint provision. *Vendor shall specify Heat up rate. | To be updated. | y | y |  | Syed Ahmed
8 | Callout | 4 | Mohamed Ayyash | Note | To be updated. | y | y |  | Mohamed Ayyash
9 | Callout | 4 | Mohamed Ayyash | Space | To be updated. | y | y |  | Mohamed Ayyash