## CRS
No. | Rev. | Page No. | author | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | Callout | 2 | Saeed Taher | Material and ASTM specifications to be specified for all components. | Noted. Will be add "ASTM". Material for each components is defined by vendor. | y | y |  | Saeed Taher
2 | Callout | 5 | Mohamed Ayyash | space between letters | To be updated. | y | y |  | Mohamed Ayyash
3 | Callout | 5 | Mohamed Ayyash | space | To be updated. | y | y |  | Mohamed Ayyash