## 044-E-DAT-00003-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
3 | Callout | Page 2 | Saeed Taher | SA 240 TP 316L | Comment incorporated | Y
4 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis. | No upset case required for higher temperature than design condition. To be reviewed with FEED/Licensor, if required. | N
5 | Callout | Page 2 | BD Mori | Corrosion allowance is deleted. FEED value is 6 mm | Header material is changed from CS to SS316L following T1133. So, corrosion allowance is not required. | Y
6 | Text Box | Page 3 | Mahdi Ali | 4TGTU | Comment incorporated | Y
7 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
8 | Callout | Page 3 | Salman Jaffer | a) Each header box shall be provided with positive isolation and inlet/outlet piping for each pay to be symmetrical. b) Please refer to Bid Query T1383 for the requirement for automatic louver c) Provide local temperature indication for each outlet. d) Type 'B' manifold. e) The degree of the slop for free draining purpose to be identified. f) Air Cooler with more than bay shall have individual isolation for each bay. | a) Will be clarified at TBE stage b) Automatic louver has been applied at datasheet for air coolers of Sulphur Block as per T1383. c) Will be clarified at TBE stage d) Will be clarified at TBE stage e) Will be clarified at TBE stage f) Will be clarified at TBE stage | N
9 | Callout | Page 3 | BD Mori | Do not use acronyms: High Severity Wet H2S Service (HSS) | Comment incorporated | Y
10 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3 | Minimum design temperature has been called many BMP specifications, especially BMPS-E7. No need to specify BMP-A3. | N