## 044-E-DAT-00003-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs
3 | Callout | Page 2 | Saeed Taher | SA 240 TP 316L
4 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis.
5 | Callout | Page 2 | BD Mori | Corrosion allowance is deleted. FEED value is 6 mm
6 | Text Box | Page 3 | Mahdi Ali | 4TGTU
7 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
8 | Callout | Page 3 | Salman Jaffer | a) Each header box shall be provided with positive isolation and inlet/outlet piping for each pay to be symmetrical. b) Please refer to Bid Query T1383 for the requirement for automatic louver c) Provide local temperature indication for each outlet. d) Type 'B' manifold. e) The degree of the slop for free draining purpose to be identified. f) Air Cooler with more than bay shall have individual isolation for each bay.
9 | Callout | Page 3 | BD Mori | Do not use acronyms: High Severity Wet H2S Service (HSS)
10 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3