## 044-E-DAT-00005-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Callout | Page 1 | Salman Jaffer | add unit name | Will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | N
3 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
4 | Cloud+ | Page 2 | Sameer.Ahmed | As per BMPS-A1 8.2.3, the standard lengths are 16ft, 30ft & 42ft | As per BMPS-A1 and BMPS-E7, preferred tube length is 16, 30, 42 ft. However, this limitation can be discussed during the EPC stage, as per Bid Clarification T883 for the economical reasons. It can be deeply discussed after TBE. | N
5 | Callout | Page 2 | balagangadhar.k | Refer FEED datasheet 2520-s044-SP-0810-07_C for 60# Blowdown Drum and cross check the operating temperature and pressure, change if required. | Operating condtion for V4414 is to be 221.5degF/3 psig. (Saturated condition) | Y
6 | Callout | Page 2 | BD Mori | Add reference to note 7 | Noted. To be revised. | Y
7 | Callout | Page 3 | Salman Jaffer | c) Type 'B' manifold. d) The degree of the slop for free draining purpose to be identified. | a) Automatic louver has been applied at datasheet for air coolers of Sulphur Block as per T1383. b) Will be clarified at TBE stage c) Will be clarified at TBE stage | N
8 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3 | Minimum design temperature has been called many BMP specifications, especially BMPS-E7. No need to specify BMP-A3. | N