## CRS
No. | Rev. | Page No. | author | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | Callout | 1 | BD Mori | The changes/additions/deletion done in the FEED documents are not highlighted by TTSJV in the data sheet. It must be highlisted as per the agreed procedure. This comments is applicable to all the data sheets /documents | Change to be highlighted. | y | y |  | BD Mori
2 | Callout | 1 | BD Mori | Comments on this data sheet are also applicable to 045U4501 | Noted. | y | y |  | BD Mori
3 | Callout | 1 | Nalini Mohan | Modify the tag number as per the latest equipment numbering convention | To be changed. | y | y |  | Nalini Mohan
4 | Callout | 1 | Mohamed Ayyash | page 1/11 correct all pages | This page is the cover with wet signature(Additional page). As per agreed procedure between BAPCO and TTSJV, deliverables are transmitted 2 types, 1) native file and 2) PDF converted file with signed cover. Without pdf signed cover page, other pages are PDF converted page. | y | y |  | Mohamed Ayyash
5 | Callout | 1 | Jeung.Kim | All data sheets have to be updated according to FEED Validation and detail design development.- typical comment | To be updated. | y | y |  | Jeung.Kim
6 | Callout | 2 | Mohamed Ayyash | correct page numbers | To be updated. | y | y |  | Mohamed Ayyash
7 | Callout | 3 | Syed Ahmed | Sweet | To be added. | y | y |  | Syed Ahmed
8 | Callout | 3 | Syed Ahmed | Sweet | To be added. | y | y |  | Syed Ahmed
9 | Callout | 3 | Syed Ahmed | Sweet | To be added. | y | y |  | Syed Ahmed
10 | Callout | 3 | Sankara | Modernization | To be corrected. | y | y |  | Sankara
11 | Callout | 4 | Salman Jaffer | modify re levent to relevant | To be corrected. | y | y |  | Salman Jaffer
12 | Callout | 4 | BD Mori | Replace with " outlet" | To be updated. | y | y |  | BD Mori
13 | Callout | 4 | BD Mori | Quantity of nitrogen flow? To be checked with Licensor. | Nitrogen flow is very small quantity, but to be checked with licensor. | y | y |  | BD Mori
14 | Callout | 5 | Syed Ahmed | General note to be added: All the equipment and control valves shall be suitably design for all the operating cases for normal and turndown operation. | Noted. | y | y |  | Syed Ahmed
15 | Callout | 6 | Salman Jaffer | Modify CO2 to (CO+CO2) per T334 | To be updated. | y | y |  | Salman Jaffer
16 | Callout | 6 | BD Mori | Vendor to specify and incorporate incinerator heating and cooling temperature rates for start-up and shutdown | Requirement to be added. | y | y |  | BD Mori
17 | Callout | 6 | Mohamed Ayyash | move | To be updated. | y | y |  | Mohamed Ayyash
18 | Callout | 6 | Saeed Taher | Vendor to propose material selection to be reviewed and approved during EPC phase. This is applicable to the whole incinerator package. | Noted. | y | y |  | Saeed Taher
19 | Callout | 7 | Syed Ahmed | Sweet | To be updated. | y | y |  | Syed Ahmed
20 | Callout | 7 | Syed Ahmed | Sweet | To be updated. | y | y |  | Syed Ahmed
21 | Callout | 7 | Salman Jaffer | Numbering of notes in this document is not consistence, just an example Note 7 is shown in sheet 6 and same number is used in sheet 7. Moreover, note 1 is shown in sheet 6 and another note 1 in sheet 10. | Note7,18 is applicable only for 'Table 4: Fuel gas' This note is coming from BMPS-A1 section 9.2. | y | y |  | Salman Jaffer
22 | Callout | 7 | Salman Jaffer | Some notes could not be found such as notes 12 and 15. Please check the notes and sequence. | Fuel gas table is coming from BMPS-A1 section 9.2. For preventing confusion, fuel condition on D/S wil be removed and call BMPS-A1. | y | y |  | Salman Jaffer
23 | Callout | 7 | Salman Jaffer | Please review the need of maintaining note 18 in this document, sour Khuff gas will not be sent to the Incinerator directly (only treated). | Note 18 is specified on BMPS-A1 section 9.2. | y | y |  | Salman Jaffer
24 | Callout | 7 | BD Mori | Revise Fuel gas details as per the latest BMPS-A1 | To be updated after receiving latest BMPS-A1. | y | y |  | BD Mori
25 | Callout | 7 | BD Mori | Delete | To be updated. | y | y |  | BD Mori
26 | Callout | 7 | Nalini Mohan | As per FEED, No.6 stream is using ejectors with 110# steam | Steam condition is changed following Clarification T1502. | y | y |  | Nalini Mohan
27 | Callout | 7 | Nalini Mohan | Mode of temperature control should be defined by EPC Contractor. | This note is just for information considering incinerator package design. To be definded by SECL. | y | y |  | Nalini Mohan
28 | Callout | 7 | Mohamed Ayyash | align on all pages | To be updated. | y | y |  | Mohamed Ayyash
29 | Callout | 7 | Mohamed Ayyash | N | To be updated. | y | y |  | Mohamed Ayyash
30 | Callout | 7 | Mohamed Ayyash | No. | To be updated. | y | y |  | Mohamed Ayyash
31 | Callout | 8 | BD Mori | This shall be considered in the down stream equipment and stack design. | Noted. | y | y |  | BD Mori
32 | Callout | 8 | BD Mori | 550# steam shall meet the purity specifications provided in BMPS-A1 | Noted. | y | y |  | BD Mori
33 | Callout | 8 | BD Mori | (supply pressure) | To be updated. | y | y |  | BD Mori
34 | Callout | 8 | Salman Jaffer | Boiler Feed Water control valve and associated bypass shall be designed adequately to ensure that vibration and erosion is prevented. | Noted. Nothing to be changed on D/S. | y | y |  | Salman Jaffer
35 | Callout | 8 | Mohamed Ayyash | . Add | To be updated. | y | y |  | Mohamed Ayyash
36 | Callout | 10 | Mohamed Ayyash | . Add | To be updated. | y | y |  | Mohamed Ayyash
37 | Callout | 10 | Saeed Taher | This is the minimum requirements, vendor to propose selection of refractory type and thickness to be reviewed and approved during EPC phase. | Noted. | y | y |  | Saeed Taher