## 047-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | balagangadhar.k | HEAT AND MATERIAL BALANCE
2 | Callout | 1 | Salman Jaffer | Source of stream 41 is (7CDU/VDU and SGPs). Delete 2HCU and TGTU because normally NNF
3 | Callout | 1 | Salman Jaffer | DCU is not part of BMP scope of work. For design purpose, please add note (as future project)
4 | Callout | 1 | balagangadhar.k | OFF
5 | Text Box | 1 | MAK | Refer to Sht. 001 for the General Comments.
6 | Callout | 1 | Salman Jaffer | In FEED PFD BRB-228474 sheet 2 of 3 rev0, Std Liquid Volumetric Flow of these stream is less than 17. Please confirm.