## 048-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 1
2 | Call-out | 1 | MAK | 2
3 | Call-out | 1 | MAK | 3
4 | Call-out | 1 | MAK | 4
5 | Callout | 1 | Syed Ahmed | Add : E
6 | Callout | 1 | BD Mori | Add chimney tray number
7 | Call-out | 1 | Hasan Al Noaimi | any changes like so should be raised to OWNER before implimintation.
8 | Callout | 1 | Salman Jaffer | Check DEMIN water supply pressure and pressure required at the injection point. Show the source including the PFD number and stream data
9 | Callout | 1 | balagangadhar.k | Check legend for symbol, this line to be deleted (typical)
10 | Call-out | 1 | MAK | Delete
11 | Call-out | 1 | MAK | Delete #
12 | Call-out | 1 | MAK | Delete the line
13 | Text Box | 1 | Syed Ahmed | General comment: Show PFD numbers
14 | Callout | 1 | Syed Ahmed | General comment: Show PFD numbers
15 | Callout | 1 | Salman Jaffer | General Comment: use full tang number
16 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
17 | Text Box | 1 | MAK | General Comments applies to all PFDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 003 on all the sheets. 3. Always use NTS for PFD scale. 4. Always use A1 for PFD border size.
18 | Callout | 1 | Syed Ahmed | keep it solid as per BMPS-A-50003 and indicate NFF
19 | Callout | 1 | Syed Ahmed | keep it solid as per BMPS-A-50003 and remove one valve.
20 | Callout | 1 | Salman Jaffer | Modify to 50# STEAM
21 | Callout | 1 | Syed Ahmed | provide equipment number
22 | Callout | 1 | balagangadhar.k | Show the connections properly, show reboiler symbol as per legend
23 | Text Box | 1 | BD Mori | This unit PFDs were prepared during FEED, This unit PFDs were prepared during FEED, based on the Licensor EDP PFDs. The PFDs were reviewed by Licensor, Bapco and FEED contractor. The process flow configuration was finalized based on the reviews, Bapco’s operating experience with similar units, lessons learned and industry best practices. The PFDs have also under gone Hazop at EDP and FEED stage. Therefore, the deletion of amine tanks, associated facilities and process modifications, to the FEED stage PFDs are not acceptable. TTSJV shall discuss any changes to the FEED PFDs and P&IDs before it is issued in EPC. TTSJV shall also clearly mark such changes and obtain Owner’s approval. If any PFD and P&ID is issued without Owner’s approval, the transmittal shall be summarily rejected.
24 | Text Box | 1 | BD Mori | Unit 048 and 049 H&M balance to be revised base on the design of 1/2 SGP.
25 | Text Box | 1 | Mahdi Ali | Unit numbers shall be 3 digits, i.e. 049. Unit abbreviations shall not contain '#'
26 | Callout | 1 | balagangadhar.k | Update all drawing numbers
27 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.