## 049-E-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs
3 | Callout | Page 2 | Saeed Taher | SA 240 TP 316L
4 | Cloud+ | Page 2 | Sameer.Ahmed | This length is not as per BMPS-A1 8.2.3
5 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis.
6 | Callout | Page 3 | Salman Jaffer | * Requirement for winterisation to be determined by detailed engineering contractor. * Please refer to Bid Query T1383 for the requirement for automatic louver * Self draining per PIDs. * Manifold type "B"
7 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3
8 | Callout | Page 3 | BD Mori | Do not use acronyms: High Severity Wet H2S Service (HSS)