## 341-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Julio.Aguilar | Existing Sahara Dryer PFD number to be indicated. If the existing PFD is not available includes a note referring PID number for details.
2 | Cloud+ | 1 | Sameer.Ahmed | FEED design to be retained. Provide battery limit with isolation valve for each branch
3 | Callout | 1 | Robert.Kawitzki | Maintain the same line thickness for new lines
4 | Call-out | 1 | Edgardo | Please indicate the document number of the connecting PFD
5 | Cloud+ | 1 | Julio.Aguilar | Please reword: "FOUR CENTRIFUGAL-TYPE AIR COMPRESSORS ARE PROVIDED, TWO ARE OPERATING, ONE IS IN STAND-BY AND ONE IS SPARE/MAINTENANCE"
6 | Callout | 1 | Julio.Aguilar | Show the compressor capacity as 7650 SCFM. The ICFM capacity of 8400 can be mentioned under Note 6.
7 | Callout | 1 | BD Mori | The instrument and yard air consumption at the FEED stage was preliminary. Therefore, TTSJV shall finalise the air consumption during EPC stage and resubmit the PFDs for Bapco approval.
8 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance