## 371-E-DAT-55001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Check sequence number!! | The number has been confirmed by J/V's Homogenization Procedure. | Y
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
3 | Cloud+ | Page 2 | Sameer.Ahmed | As per BMPS-A1 8.2.3, O.D. 25.4 (1) | Tube OD can be used from 1 inch to 1.5 inch, as per BMPS-E7 para. F.2.4.2 | N
4 | Callout | Page 3 | Julio.Aguilar | Add: according to BMPS-A3. | Minimum design temperature has been called many BMP specifications, especially BMPS-E7. No need to specify BMP-A3. | N
5 | Cloud+ | Page 3 | Julio.Aguilar | Replace"MFR" by "Supplier" throughout the whole document | Comment incorporated. | Y
6 | Callout | Page 3 | Julio.Aguilar | Add: according to BMPS-A3. | No need to specify BMP-A3. | N
7 | Cloud+ | Page 3 | Julio.Aguilar | To be removed | Comment incorporated. | Y
8 | Callout | Page 3 | Julio.Aguilar | Please consider to include additional notes saying: "20) Type B manifold." | Will be clarified with vendor during TBE. | N