## 010-G-DAT-00015-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | 986131 | Process data to be reviewed based on flare summary report and UFD. Currently these documents are not available.
26 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
2 | Text Box | 2 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
5 | Call-out | 2 | Ahmed Ali | service: Flare K.O Drum not Heavy Naphtha
7 | Callout | 2 | alexis.martinez | Page 2, rows 32/33. Inconsistency of max. ambient temperature and relative humidity shown in page 2 and page 7. Review and correct accordingly.
8 | Callout | 2 | alexis.martinez | Page 2. Relative density and viscosity properties does not match with FEED data sheet. Review and correct accordingly.
10 | Callout | 2 | Fernando.Perez | Use capital letters "NOMINAL"
11 | Callout | 2 | Fernando.Perez | Service is "Flare K.O. Drum"
12 | Callout | 2 | Fernando.Perez | Page 7 says 113 F
13 | Callout | 2 | Fernando.Perez | Acc. Feed NPSHa is 10 mts Check and confirm
14 | Callout | 2 | Fernando.Perez | H2S content to be specified. Call for NOTE 4
15 | Callout | 2 | Fernando.Perez | Apply 2/8
16 | Callout | 2 | Fernando.Perez | Should be Group II
17 | Callout | 2 | Fernando.Perez | Acc BMPS-A1 CW Inlet Press is 65 psig
18 | Callout | 2 | Fernando.Perez | Overlap, Correct it
27 | Cloud+ | 2 | Mohamed Ayyash | Avoid overlap with table lines.
28 | Cloud+ | 2 | Mohamed Ayyash | Cooling water is the stream name and not the source. Need to specify the plant where it is coming from.
29 | Cloud+ | 2 | Mohamed Ayyash | Use page no. 2/9 and not 2. Apply this to all pages
19 | Callout | 3 | Fernando.Perez | Grouted recommended by API 610 Paragraph 7.3.8
20 | Callout | 3 | Fernando.Perez | Drain shall be Flanged & Valved. min. size 3/4"
21 | Callout | 3 | Fernando.Perez | ISO VG 68 to be taken into account
22 | Callout | 3 | Fernando.Perez | Aligne with the rest
35 | Callout | 3 | Yousif Ahmadi | Per API, S-8 impeller is SS316. Check and confirm
23 | Callout | 4 | Fernando.Perez | Check for Dual Pressurized Seal
24 | Callout | 5 | Fernando.Perez | Correct the overlaping
30 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
31 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
32 | Cloud+ | 5 | Mohamed Ayyash | Align, use justify from the left
6 | Text Box | 6 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. In the RFI, all applicable BMPS-J series to be referenced (such as J2, J3 â€¦etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractorâ€™s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be finalized in consultation with the supplier. 6. Supplier to be notified on consideration of the Automatic Operation of the pumps based on the vessel level and Start Permissive (linked temperature measurement) requirements per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. If applicable, all the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided in clientâ€™s standard format for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting â€¦etc shall be installed by the ven-dor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 17. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
25 | Callout | 7 | Fernando.Perez | Page 2 says 110 F
33 | Cloud+ | 7 | Mohamed Ayyash | This is site location and not unit names. Need to mention units names.
3 | Call-out | 8 | Abdulaziz | Flush point and auto ignition temperature figures to be corrected and confirmed
4 | Text Box | 8 | Abdulaziz | M/SEAL vendor shall be provided with operating parameter during, start-up/shutdown mode, study state condition an upset in order to provide the optimum design selection.
9 | Callout | 8 | alexis.martinez | Page 8, Note column. The number of the notes is located in the column used to identify the rows in the page. Move the notes numbers to the corresponding note
34 | Callout | 8 | Sankara | LV Motors to follow P19