## 010-L-PPN-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Add the word "COLUMN"
2 | Cloud+ | 1 | Mohamed Ayyash | Change to small letters
3 | Cloud+ | 1 | Mohamed Ayyash | Change to small letters
4 | Callout | 1 | Erwin.Lugue | Check sufficient headroom clearances & requirement for overhead lifting for maintenance
5 | Callout | 1 | Erwin.Lugue | Check sufficient headroom, spacing, clearances & requirement for overhead lifting for maintenance
6 | Callout | 1 | Erwin.Lugue | Check sufficient headroom, spacing, clearances & requirement for overhead lifting or monorail for maintenance
7 | Callout | 1 | Robert.Kawitzki | Confirm access around equipment including associated piping - typ comment
8 | Callout | 1 | Erwin.Lugue | corresponds
9 | Callout | 1 | Berik.Nurbolatov | GENERAL :Please ensure that 3 off decimals are used in elevation EL.
10 | Text Box | 1 | alexis.martinez | General: All Equipment Numbers need to be updated as per the new numbering provided by owner. Review an d correct accordingly.
11 | Callout | 1 | Berik.Nurbolatov | GENERAL; Please arrange distance data b/ n grids , units. This will reload the overcrowded information given in main plot plan.
12 | Callout | 1 | Erwin.Lugue | HPP Elevation?- typ comment
13 | Callout | 1 | Erwin.Lugue | HPP Elevation?- typ comment
14 | Callout | 1 | Erwin.Lugue | Indicate handrails in the structures-typ comment
15 | Callout | 1 | Erwin.Lugue | Indicate in plans the extent of the grating
16 | Text Box | 1 | Erwin.Lugue | Missing dimensions between grids- typ. comment
17 | Callout | 1 | Erwin.Lugue | Missing elevations of crane & roof
18 | Callout | 1 | Erwin.Lugue | Missing elevations of platforms
19 | Text Box | 1 | Erwin.Lugue | Missing plans & elevation for P010PSTR800
20 | Callout | 1 | Berik.Nurbolatov | Please mention HPP EL. relative to the site datum.
21 | Callout | 1 | Berik.Nurbolatov | Please put the pumps as per 010--PPN-00001-001
22 | Callout | 1 | Berik.Nurbolatov | Please put the pumps as per 010--PPN-00001-001
23 | Callout | 1 | Berik.Nurbolatov | Please remove the plant orientation data as current plot plan is supplementary of the 010-L-PPN-00001-001. The reference can be made via grid data, elevation and rack name.
24 | Callout | 1 | Berik.Nurbolatov | Plot plans shall be dimensioned in metric units (mm) of linear measurement (refer BMPS A8 ‘General guidelines of Plot plan layout Part B Appendix B1 page 66)
25 | Callout | 1 | Erwin.Lugue | Provision for removable handrails for maintenance
26 | Callout | 1 | Erwin.Lugue | Refer to BMP-CON-LET-00047
27 | Callout | 1 | Erwin.Lugue | relative
28 | Callout | 1 | Erwin.Lugue | relative
29 | Callout | 1 | Erwin.Lugue | Reorganize grid numbering system
30 | Callout | 1 | Erwin.Lugue | Shelter partially or fully enclosed?
31 |  | 1 | AutoCAD SHX Text | The present document or drawing is property of TECHNIP ITALY S.p.A. and shall not. under any circumstances. be totally or partially. directly or indirectly. transferred. reproduced. copied. disclosed or used. without its prior written consent. for any purpose and in any way other than that for which it is specifically furnished or outside the extent of the agreed upon right of use.
32 | Text Box | 1 | RASHED SHOWAITER | TR to demonstrate the initial rigging study for maintenance and T&Is (post construction) and to consider the following: •Crane position and trailers for unloading and loading exchangers. •Crane position and trailers for exchangers using bundle-puller. •Crane position for vessels random packing. •Crane position for unloading and loading vacuum column structured packing. •Laydown assembly area for vacuum column structured packing. •Lifting of heavy control valves. •Lifting of RVs. •Lifting of pumps. •Crane position and trailers for fin fan bundles.
33 | Cloud+ | 1 | Mohamed Ayyash | Typo. Correct equipment number
34 | Cloud+ | 1 | Mohamed Ayyash | Typo. Should read 2nd
35 | Cloud+ | 1 | Mohamed Ayyash | Typo. Should read 2nd
36 | Callout | 1 | Erwin.Lugue | Verify crane lifting clearance & capacity
37 | Callout | 1 | Erwin.Lugue | Verify requirement for access platform
38 | Callout | 1 | Erwin.Lugue | Verify requirement for removable roofing panels
39 | Callout | 1 | Erwin.Lugue | Verify requirement for secondary egress as per BMPS A5
40 | Callout | 1 | Erwin.Lugue | Verify requirement for secondary egress as per BMPS A5