## 017-G-DAT-00017-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Isamu | Delete
2 | Text Box | 1 | 986131 | Process data to be reviewed after the unit study is completed and accepted.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Text Box | 1 | Isamu | Use project finalized cover page for data sheet
7 | Call-out | 2 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
8 | Callout | 2 | Fernando.Perez | call to NOTE 14
9 | Callout | 2 | Isamu | Delete
10 | Callout | 2 | Isamu | Line is asking you about the source ?? correct please
11 | Callout | 2 | Isamu | Number on all sheets
12 | Callout | 2 | alexis.martinez | Page 2, rows 32/33. Inconsistency of maximum ambient temperature and relative humidity shown in page 2 and page 8. Review and correct
13 | Callout | 2 | Fernando.Perez | Page 7 include 113 F, check
14 | Callout | 2 | Isamu | Please double check if this value includes positive atmo pressure and negative vapor proessure
15 | Callout | 2 | Fernando.Perez | Should be Group II, Check
16 | Callout | 2 | Fernando.Perez | Use Capital "NOMINAL"
18 | Callout | 3 | Fernando.Perez | ISO VG 68 to be taken into account
19 | Call-out | 3 | Abdulaziz | Maximum operating temperature as per note (6) is 150 F. To checked and confirm.
20 | Callout | 4 | Fernando.Perez | Check Drain requirement as VS4 type pump. Check Cooling Water requirement
21 | Callout | 4 | Fernando.Perez | Check Dual Pressurized & Plan 53A as per H2S concentration, and per Gas dissolved in the fluid.
22 | Callout | 4 | Fernando.Perez | Check if Plan M is required
23 | Callout | 4 | Fernando.Perez | This shall has NOTE #
25 | Cloud+ | 5 | Mohamed Ayyash | ???
26 | Cloud+ | 5 | Mohamed Ayyash | Align, use justify from the left
27 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap. Can continue on the next line.
28 | Callout | 5 | Fernando.Perez | Avoid overlaping
29 | Callout | 5 | Fernando.Perez | Avoid Overlaping
30 | Cloud+ | 5 | Yousif Ahmadi | Witness
31 | Callout | 5 | Yousif Ahmadi | YES
33 | Cloud+ | 6 | Mohamed Ayyash | Delete line
34 | Call-out | 6 | Abdulaziz | TR to confirm with supplier as this is a submersible pump VS4.
35 | Callout | 7 | Fernando.Perez | Include standard where Table 11 is included
36 | Text Box | 7 | Ahmed Marhoon | This datasheet is related to SGP unit which is under process simulation and hence the design is not fully developed as of the date of this issue. In any case, the following comments are provided for consideration where the final review/comments can be done after finalizing the process design: 1. No notes have been found for the instrumentation & control scope on this Datasheet. The RFI needs to cover all the applicable BMPS-J specifications for the supplier to comply with, if applicable. 2. Scope of supply for the interposing relays to be clearly defined. 3. Supplier to be notified on consideration of mode of operation operation (Auto start-stop vs. auto stop vs. manual ...etc) linked to the a feedback signal and any Permissive to start signals linked to process variables such as temperature measurement. The final control and machine protection scheme shall be based on the final PID post detail design, vendor recommendations and agreement on the general item regarding operation of the sump pumps. 4. Since the Datasheets are issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Datasheet and vice versa.
37 | Callout | 8 | Fernando.Perez | Page 7 include 110 F, check
38 | Cloud+ | 8 | Mohamed Ayyash | This is a site location and not unit names. It is asking for service for units and therefor need to mention those units names.
39 | Callout | 9 | Fernando.Perez | Acc BMPS-G2 Parag.6.1.8 Table 1a, NPSHr shall be less than 55% of NPSHa for Amine services
40 | Text Box | 9 | Abdulaziz | M/SEAL vendor shall be provided with operating parameter during, start-up/shutdown mode, study state condition an upset in order to provide the optimum design selection.
41 | Callout | 9 | Fernando.Perez | This fluid will get more than 3% of H2S when Flashing to atmosphere. Check
42 | Cloud+ | 9 | Mohamed Ayyash | Wrong vessel name. Should be " Amine Sump Drum"