## 019-E-DAT-00038-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Typewritten Text | 1 | Mohamed Ayyash | General comment: Many text fonts are small and unreadable. Need to enlarge.
2 | Text Box | 1 | Mahdi Ali | Remove letter 'c'
3 | Text Box | 1 | MAK | Use the latest document cover page template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
4 | Call-out | 2 | A.Jabbar Mahmood | enlarge font size for clarity
5 | Callout | 2 | Yousif Ahmadi | Minimum
6 | Call-out | 2 | Abdulaziz | Missing information to be provided
7 | Callout | 2 | Yousif Ahmadi | Note (6, 17 ,18)
8 | Callout | 2 | Yousif Ahmadi | Per FEED it is plug type. TR to clarify tthe double plug type selection
9 | Cloud+ | 2 | A.Jabbar Mahmood | TR to add a note reporting the air conditions (temp, density and barometric pressure) on which this value based on.
10 | Call-out | 2 | Abdulaziz | TR to clarify no. of vibration switch on the finfans bundle/bank
11 | Text Box | 4 | Ahmed Marhoon | 1. Reference to note 14: The scope for instrumentation and control is not limited to the alarms in DCS only. All the control functions will be done in the DCS with the necessary interconnections with the electrical MCC. A clear note to be added to emphasize on having the temperature control by the outlet temperature measurement. The final design of the system shall be based on the BMPS specifications (including relevant J class) and the final PID post detail design and Hazop3/SIL analysis. Suppliers to be instructed accordingly. This is a typical comment for all fin fan air coolers. 2. Contractor to add reference to the applicable BMPS specifications such as BMPS-P20/P21 and relevant BMPS-J specifications. Typical for all air coolers with Variable Speed Drives.
12 | Text Box | 4 | Omran A | As per BMPS-J36, BMPS-J37 & BMPS-J38
13 | Call-out | 4 | A.Jabbar Mahmood | Correct font size of Note 8
14 | Text Box | 4 | Abdulaziz | Fin fan shaft bearings shall be furnished with vibration sensors that are connected to a junction box e.g. Switch Box SB 202 with 48 channels provided at platform. This will provide convenient provision to collect the vibration data using 2140 portable vibration analyzer.
15 | Cloud+ | 4 | A.Jabbar Mahmood | The reported fluid composition and the air cooler design are based on Operating Case EOR. Amend
16 | Text Box | 4 | Mahdi Ali | Use Bapco number