## 019-E-DAT-00048-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Typewritten Text | 1 | Mohamed Ayyash | General comment: Many text fonts are small and unreadable. Need to enlarge.
2 | Text Box | 1 | Mahdi Ali | Remove letter 'c'
3 | Text Box | 1 | MAK | Use the latest document cover page template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
4 | Call-out | 2 | Abdulaziz | Missing information to be provided
5 | Callout | 2 | Yousif Ahmadi | Should be FRP
6 | Call-out | 2 | Abdulaziz | TR to clarify no. of vibration switch on the finfans bundle/bank
7 | Text Box | 3 | Ahmed Marhoon | 1. Reference to note 14: The scope for instrumentation and control is not limited to the alarms in DCS only. All the control functions will be done in the DCS with the necessary interconnections with the electrical MCC. Interlock with the pumps running status to be also stated (START/STOP). The final design of the system shall be based on the BMPS specifications (including relevant J class) and the final PID post detail design and Hazop3/SIL analysis. Suppliers to be instructed accordingly. This is a typical comment for all fin fan air coolers. 2. Contractor to add reference to the applicable BMPS specifications such as BMPS-P20/P21 and relevant BMPS-J specifications. Typical for all air coolers with Variable Speed Drives.
8 | Callout | 3 | Yousif Ahmadi | Add Note per Feed data sheet "Two fans per bay shall be provided as minimum"
9 | Call-out | 3 | A.Jabbar Mahmood | As discussed during the P&ID review, the flushing requirement was proposed by the FEED contractor towards the end of FEED and hence the owner has not fully analyzed and reviewed this addition (this change was not even Hazoped). TR evaluation of the following is required: 1- CLG needs to be consulted on whether this flushing requirement is required. Unnecessary flushing will result in excessive wastage of flushing oil (diesel). 2- Whether flushing needs to be on "automatic" basis or manual flushing is sufficient, to be used as needed. 3- The stream temperature is 400 F, which might be too high for flushing diesel. TR to check the suitability of diesel flushing at the operating conditions. The final arrangement will need to be further analyzed during Hazop 3. The above note shall be modified accordingly.
10 | Text Box | 3 | Omran A | As per BMPS-J36, BMPS-J37 & BMPS-J38
11 | Cloud+ | 3 | A.Jabbar Mahmood | As per the P&IDs, 60# steam is used for the winterizing coil. Anyway, as discussed TR is supposed to evaluate using 60# versus 110# steam and confirm which one provides better performance considering the steam conditions. Accordingly, this datasheet and P&IDs shall be updated.
12 | Call-out | 3 | Sameer Foujdar | Automatic flushing of the air cooler is a new information not shared with client. Also there is no note in the P&ID. TR to clarify the need of this.
13 | Call-out | 3 | Sameer Foujdar | Correct the pump no to P0023A/B
14 | Text Box | 3 | Abdulaziz | Fin fan shaft bearings shall be furnished with vibration sensors that are connected to a junction box e.g. Switch Box SB 202 with 48 channels provided at platform. This will provide convenient provision to collect the vibration data using 2140 portable vibration analyzer.
15 | Text Box | 3 | A.Jabbar Mahmood | Review and consider the requirement of skin temperature measurement for monitoring and control to avoid congealing
16 | Call-out | 3 | A.Jabbar Mahmood | TR to clarify the basis fot this note.
17 | Text Box | 3 | Mahdi Ali | Use Bapco number