## 019-E-DAT-00049-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Typewritten Text | 1 | Mohamed Ayyash | General comment: Many text fonts are small and unreadable. Need to enlarge.
2 | Text Box | 1 | Mahdi Ali | Remove letter 'c'
3 | Text Box | 1 | MAK | Use the latest document cover page template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
4 | Cloud+ | 2 | A.Jabbar Mahmood | It is 24541 lb/h basis FEED and licensor D/S. Clarify the basis for this slight change for owner's understanding
5 | Callout | 2 | Yousif Ahmadi | Minimum
6 | Call-out | 2 | Abdulaziz | Missing information to be provided
7 | Call-out | 2 | Abdulaziz | Missing information to be provided
8 | Callout | 2 | Yousif Ahmadi | Per FEED it is plug type. TR to clarify tthe double plug type selection
9 | Call-out | 2 | Abdulaziz | TR to clarify no. of vibration switch on the finfans bundle/bank
10 | Callout | 3 | Yousif Ahmadi | Add note 10 of feed data sheet: "Two fans per bay shall be provided as minimum"
11 | Text Box | 3 | Omran A | As per BMPS-J36, BMPS-J37 & BMPS-J38
12 | Cloud+ | 3 | A.Jabbar Mahmood | Based on 400 pisg Max operating pressure, the calculated H2 pp is 414.7*0.999 = 415 psia. Check and update
13 | Cloud+ | 3 | A.Jabbar Mahmood | Based on query T132, the M/U comp suction design pressure will be upgraded to 490 psig (agreed by TR basis the P&IDs Review MoM). Hence the max design H2 pp shall be 504 psia. Check and update
14 | Text Box | 3 | Abdulaziz | Fin fan shaft bearings shall be furnished with vibration sensors that are connected to a junction box e.g. Switch Box SB 202 with 48 channels provided at platform. This will provide convenient provision to collect the vibration data using 2140 portable vibration analyzer.
15 | Callout | 3 | Yousif Ahmadi | Per FEED data sheet: "Tube to tubesheet joint shall be expanded with grooves"
16 | Text Box | 3 | Mahdi Ali | Use Bapco numbers
17 | Text Box | 3 | Ahmed Marhoon | With reference to note 9, the scope for instrumentation and control is not limited to the alarms in DCS. All the control functions will be done in the DCS with the necessary interconnections with the electrical MCC. The final design of the system shall be based on the BMPS specifications (including relevant J class) and the final PID post detail design and Hazop3/SIL analysis. Suppliers to be instructed accordingly.