## 019-K-DAT-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud | 1 | A.Jabbar Mahmood
2 | Cloud+ | 1 | A.Jabbar Mahmood | Correct pump no to 019P0005B and turbine no. to 019T0005B
3 | Text Box | 1 | Mahdi Ali | Incorrect Material Class. Should be 'G'
4 | Arrow | 1 | Mahdi Ali
5 | Text Box | 1 | MAK | General Comment: MOC shall coordinate with JV Directorate for the latest document template and updated API datasheet template.
6 | Text Box | 1 | A.Jabbar Mahmood | General: Owner has not received the revised hydraulic calculations and there cannot verify the updated pump suction, discharge pressures, design pressures and NPSHa.
7 | Call-out | 1 | MAK | Delete S
8 | Text Box | 2 | Mahdi Ali | Remove letter 'c'
9 | Cloud+ | 2 | Mohamed Ayyash | Use 2/4 (as in page one). Apply to all pages.
10 | Cloud+ | 2 | Mohamed Ayyash | Delete the word reflux
11 | Cloud+ | 3 | Mohamed Ayyash | Misplaced. Move back in line with other yellow cells
12 | Cloud+ | 3 | Mohamed Ayyash | Delete
13 | Cloud+ | 3 | Mohamed Ayyash | missing text
14 | Cloud+ | 3 | Mohamed Ayyash | Missing letter
15 | Cloud+ | 4 | Mohamed Ayyash | ??
16 | Cloud+ | 4 | Mohamed Ayyash | Avoid overlap with table lines.
17 | Cloud+ | 4 | Ahmed Marhoon | Peak 150 has been specified based on the model number mentioned on the BMPS-K5. However, with the Woodward latest model Peak200 available in the market which is replacing Peak150, will Peak150 still be supported and not going to be at the end of its life-cycle by the end of the project? TTSJV to verify with the supplier and advise the client for review and approval. Typical comment. Also, ensure to include BMPS-J18 in addition to other specifications in the RFI.