## 019-S-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdulaziz | Pumps tag number to be indicated
2 | Text Box | 1 | A.Jabbar Mahmood | TR to refer item 69 (BMP General P&ID comment) of the IssueLog-2HCU-rev1 as part of MOC-BMM-MOM-000002 and incorporate the requirements in this D/S.
3 | Callout | 2 | Fernando.Perez | Material selection according fluid handled
4 | Call-out | 2 | Abdulaziz | Missing information to be added
5 | Cloud+ | 2 | A.Jabbar Mahmood | Owner has not received the hydraulic calculations and hence cannot verify the delivery pressure. However, it is assume that the delivery pressure may change based on the final hydraulic calculations.
6 | Cloud+ | 3 | A.Jabbar Mahmood | "required for Diesel Product from a hydrocracking unit"
7 | Text Box | 3 | A.Jabbar Mahmood | Add note stating the basis used for defining the capcity of the pump inline with note 3 of the FEED D/S. Vendor shall be requested to confirm the pump capacity.
8 | Cloud+ | 3 | A.Jabbar Mahmood | Correct to 31.5 inches
9 | Call-out | 3 | A.Jabbar Mahmood | no space
10 | Call-out | 3 | Abdulaziz | Supplier to assure the performance of the pump in similar application and duty point. Also to confirm the suitability for intermittent operation/ ideal for long period.
11 | Text Box | 3 | A.Jabbar Mahmood | TR to advise why notes 12, 13 and 14 of FEED D/S is not included.
12 | Call-out | 3 | Abdulaziz | TR to confirm regarding the warehouse spare
13 | Call-out | 3 | Ahmed Ali | typo, it is
14 | Call-out | 3 | Abdulaziz | Typo: liters