## 036-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | balagangadhar.k | Comments on this datasheet are also applicable to 037C0001 with transmittal No. BMP-SOC-TRI-00123
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Sang.Hwang | Add a note if any dimension is not ft-lb since all dimensions on page 4 in SI. This is typical for all data sheet
5 | Callout | 2 | Sang.Hwang | Add N
6 | Callout | 2 | Saeed Taher | Add Note (8)
7 | Text Box | 2 | Sang.Hwang | All blank terms must be filled up with verified data unless they are not applicable. (typ. comment). In addition, in case of not applicable, blank shall be marked up with "N/A" or "-" or added a note "refer to specific mechanical drawing".
8 | Callout | 2 | Saeed Taher | ASTM specification of nuts to be specified
9 | Callout | 2 | balagangadhar.k | change to wt% & vol% from %wt & %vol, for consistency with other documents
10 | Callout | 2 | Saeed Taher | Confirm if Note (10) is applicable for removable internals , assumed not welded
11 | Callout | 2 | Sang.Hwang | Contractor to mark up clearly
12 | Callout | 2 | Sang.Hwang | Contractor to specify preliminary thickness
13 | Callout | 2 | Sang.Hwang | Fill up or make a note "refer to specific mechanical drawing"
14 | Callout | 2 | Saeed Taher | Material of skirts & supports shall be as per BMPS-C2 Para 5.6.4
15 | Cloud+ | 2 | BD Mori | Provide this data.
16 | Callout | 2 | Saeed Taher | Specify material, ASTM specification & grade for nozzles with Notes (8,10)
17 | Callout | 2 | Sang.Hwang | Top of skirt material shall be same as that of shell. Please separate skirt material for top/bottom.
18 | Callout | 2 | balagangadhar.k | Why External pressure is negative?
19 | Callout | 3 | balagangadhar.k | BMPS-C10 is applicable for valve trays
20 | Callout | 3 | balagangadhar.k | by vendor?
21 | Callout | 3 | Sang.Hwang | Mark up clearly
22 | Callout | 3 | balagangadhar.k | No.
23 | Text Box | 3 | JaiMun.Oh | The external surface shall be painted as per BMPS-B5.
24 | Callout | 3 | Sang.Hwang | To be filled up
25 | Callout | 4 | BD Mori | add : OIL
26 | Callout | 4 | Syed Ahmed | Check with vendor the requirement for providing a drain or flash point.
27 | Callout | 4 | Sang.Hwang | Contractor to specify demister design requirement such as flow rate, pressure drop, density etc.
28 | Callout | 4 | Sang.Hwang | Draw skirt and specify preliminary height
29 | Callout | 4 | BD Mori | Indicate bed limiter as per note 15
30 | Text Box | 4 | balagangadhar.k | Is Liquid distributor required? Add a note if required.
31 | Callout | 4 | BD Mori | Specify the type of inlet distributor if applicable per licensor specification
32 | Callout | 4 | Dowon Pyun | To be shown "T.L" on this line and, in connection with this, packing depth on bottom head shall be exactly shown.
33 | Callout | 5 | BD Mori | add : OIL
34 | Text Box | 6 | Sang.Hwang | All nozzles shall be integrally reinforced type.
35 | Callout | 6 | Syed Ahmed | based on the H2S concentration in the overhead gas;
36 | Text Box | 6 | Syed Ahmed | ESD
37 | Callout | 6 | Syed Ahmed | If the top feed point is used, a lower H2S-concentration can be achieved but the selectivity over CO2 is reduced. If the lower feed point is used higher H2S-content is expected at the top of the absorber but the H2S selectivity (over CO2) will be higher.
38 | Text Box | 6 | balagangadhar.k | M/H
39 | Text Box | 6 | balagangadhar.k | MANWAY
40 | Text Box | 6 | balagangadhar.k | manways
41 | Text Box | 6 | balagangadhar.k | SWEET KHUFF
42 | Callout | 6 | Sang.Hwang | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheet.
43 | Text Box | 7 | Nalini Mohan | Note numbers should be continuous.
44 | Text Box | 7 | balagangadhar.k | specify in ft (mm)
45 | Callout | 7 | Dowon Pyun | The requirement is duplicated and properly deleted or modified