## 037-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on 036C0001 (TR No. : BMP-SOC-TRI-00122) shall be applied for this item. Please be advised that Company does not re-write them for this item.
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Saeed Taher | Add Note (8)
5 | Callout | 2 | Saeed Taher | ASTM specifications of nuts to be specified
6 | Callout | 2 | Saeed Taher | Confirm if Note (10) is applicable for removable internals, assumed not welded
7 | Callout | 2 | Saeed Taher | Material of skirts & supports shall be as as per BMPS-C2 Para 5.6.4
8 | Callout | 2 | Salman Jaffer | Refer to Bid Query T1525
9 | Callout | 2 | Saeed Taher | Specify material, ASTM specification & grade for nozzles with Notes (8,10)
10 | Text Box | 3 | JaiMun.Oh | The external surface shall be painted as per BMPS-B5.
11 | Callout | 4 | Syed Ahmed | Check with vendor the requirement for providing a drain or flash point
12 | Callout | 4 | BD Mori | Indicate bed limiter as per note 15.
13 | Callout | 4 | BD Mori | Specify the type of inlet distributor if applicable per licensor specification
14 | Callout | 6 | Syed Ahmed | based on the H2S concentration in the overhead gas
15 | Text Box | 6 | Syed Ahmed | ESD
16 | Callout | 6 | Syed Ahmed | If the top feed point is used, a lower H2S-concentration can be achieved but the selectivity over CO2 is reduced. If the lower feed point is used higher H2S-content is expected at the top of the absorber but the H2S selectivity (over CO2) will be higher.