## 037-C-GAD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on 036C0001 (TR No. : BMP-SOC-TRI-00126) shall be applied for this item whatever is applicable.
2 | Call-out | 1 | Ali Abbas | General comment for instrumentation
3 | Callout | 1 | Saeed Taher | Material to be specified
4 | Callout | 1 | Sang.Hwang | Materials shall be same as that of shell.
5 | Callout | 1 | Saeed Taher | Specify material if any
6 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO this drawing shall include all the updated details and be in code 2 approval status
7 | Callout | 1 | Sang.Hwang | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This is in general for all data sheet
8 | Callout | 1 | Saeed Taher | Why NACE material not used