## 037-C-GAD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Basheer.isa | General Instrumentation specification BMPS-J02 to be added for the process connection for instruments.
2 | Text Box | 1 | Sang.Hwang | All comments shown on 036C0001 (TR No. : BMP-SOC-TRI-00126) shall be applied for this item.
3 | Callout | 1 | Saeed Taher | Material selection as per BMPS-A26
4 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO this drawing shall include all the updated details and be in code 2 approval status