## 041-C-DAT-00002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | BD Mori | Comments on this data sheet are also applicable to 042C0002R and 043C0002R
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Saeed Taher | Add (Note 12)
5 | Callout | 2 | Sang.Hwang | (add note) below
6 | Callout | 2 | Saeed Taher | Change to smls
7 | Text Box | 2 | Sang.Hwang | All blank must be filled with verified data or marked up with "N/A" or "-" or make a note to "refer to specific mechanical drawing" unless they are not applicable. (typical comment)
8 | Callout | 2 | Sang.Hwang | No space
9 | Callout | 2 | Sang.Hwang | Delete this note since note (15) has been deleted
10 | Callout | 2 | Saeed Taher | Change Note 13 to 12
11 | Text Box | 2 | balagangadhar.k | Specified FV at Design Pressure in P&ID and also refer to BMPS-A3
12 | Text Box | 3 | Sang.Hwang | In case there is any conflict between FEED document and Licensor's document, Contractor has to clarify and confirm with Licensor. In the Licensor's data sheet, there is a note for MH3/MH4 mentioning "Allow access to manways for catalyst dumping / removal. Manways to be positioned below center of reactor". Please re-check this point and correct.
13 | Callout | 3 | Sang.Hwang | No.
14 | Callout | 3 | Sang.Hwang | Insulation thickness to be re-checked as per BMPS-N1
15 | Callout | 3 | BD Mori | This is already covered in the statement above this line. Therefore, check and if not required delete.
16 | Text Box | 3 | Sang.Hwang | 10. Please add note regarding the MPT (Minimum Pressurizing Temp) to specify the temperature and pressure.
17 | Callout | 3 | BD Mori | The thermocouples installed in the catalyst bed shall read the temperatures at 75%, 50% and 25% from the top of the catalysts bed. However, as per the dimensions provided in this note, the thermocouples located from top of the catalyst bed at 150 mm, 510 mm and 850 mm will read temperature at 85%, 50% and 17% from the top of the catalyst bed. Consult Licensor and make correction as required for providing the temperature reading at 75%, 50% and 25% from the catalyst bed top.
18 | Callout | 3 | Sang.Hwang | delete this standard
19 | Callout | 3 | BD Mori | Refer note 14 on page 4 on addition of 150 mm of ½” diameter ceramic balls on top of the catalyst bed. Therefore, check and confirm with Licensor, is 6” height of 2” (50 mm) refractory lining is from top of the catalyst bed or from the top of the ceramic balls?
20 | Callout | 4 | Sang.Hwang | The instrument size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheets.
21 | Callout | 4 | Sang.Hwang | Contractor shall specify it clearly.
22 | Text Box | 4 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
23 | Callout | 4 | Sang.Hwang | Is ti necessary to indicate like this way? Please check and delete it.
24 | Callout | 4 | Salman Jaffer | Add heading for the proposed catalyst supplier table
25 | Callout | 4 | Sang.Hwang | w/impingement baffle
26 | Callout | 4 | Sang.Hwang | Hardness value shall be re-checked as per applicable specifications and corrected
27 | Text Box | 4 | Dowon Pyun | Contractor to add a typical note as "All kinds of thickness and weight terms shown in this data sheet shall be verified by strength calculations".