## 041-E-DAT-00002-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Sang.Hwang | Not only
2 | Text Box | 1 | BD Mori | Process comments on this data sheet are also applicable to 041E0003 and 041E0004
3 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC Contractor shall coordinate with JV Directorate.
4 | Callout | 1 | Sang.Hwang | but also all other comments
5 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
6 | Text Box | 1 | Sang.Hwang | In addition, all comments shall be applied for all other unit 042/043/044/045 but refractory requirement will not be applied for unit 044/045.
7 | Text Box | 2 | Dowon Pyun | All blanked terms must be filled with verified data unless they are not applicable. (Typ. comment)
8 | Callout | 2 | Dowon Pyun | Contractor to confirm if over design margin is included or not and its condition should be noted (Typ. comment)
9 | Text Box | 2 | Sang.Hwang | In case they are not applicable, please mark up "N/A" or "-" . If necessary, make a note "refer to specific mechanical drawing"
10 | Callout | 2 | Sang.Hwang | Over design margin to be re-confirmed by the Licensor
11 | Callout | 2 | Sang.Hwang | TEMA type to confirmed by the Licensor
12 | Callout | 3 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
13 | Callout | 3 | Nalini Mohan | As per Note 14 design pressure for internal explosion is 100psig. Since internal explosion is applicable on channel side please advise which components (list them) on channel are specifically designed for 100psig and 50psig (with 90% yield strength during explosion)
14 | Callout | 4 | Saeed Taher | Add 'CS'
15 | Callout | 4 | Dowon Pyun | Add 'Note 1'
16 | Callout | 4 | Saeed Taher | Specify ASTM specification & grade
17 | Callout | 4 | Saeed Taher | Add 'CS + Refractory Lined (Note 1,28)'
18 | Callout | 4 | Saeed Taher | Add 'Refractory Lined'
19 | Arrow | 4 | Dowon Pyun
20 | Callout | 4 | Saeed Taher | Add 'SA285GRC'
21 | Callout | 5 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
22 | Text Box | 6 | Salman Jaffer | STUB
23 | Callout | 6 | Jong.Ahn | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheet.
24 | Text Box | 6 | Salman Jaffer | WELD
25 | Text Box | 6 | Salman Jaffer | WELD
26 | Text Box | 6 | Salman Jaffer | STUB
27 | Callout | 9 | Syed Ahmed | In addition, vane pack demister shall be design to be easy for removal and install back during T&I.
28 | Callout | 9 | balagangadhar.k | No. (Typical for all datasheets)
29 | Text Box | 9 | JaiMun.Oh | Paint shall be performed as per BMPS-B5.
30 | Callout | 9 | Dowon Pyun | Base material and HAZ should have the same hardness value, which shall be evaluated with the severity of process service conditions.