## 041-E-DAT-00004-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on 041E0002 shall be applied for this item. Please be advised that Company does not re-write all comments for this item.
2 | Callout | 1 | balagangadhar.k | NO.3
3 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC Contractor shall coordinate with JV Directorate.
4 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
5 | Text Box | 6 | Salman Jaffer | STUB
6 | Text Box | 6 | Salman Jaffer | STUB
7 | Text Box | 6 | Salman Jaffer | WELD
8 | Text Box | 6 | Salman Jaffer | WELD
9 | Callout | 6 | Jong.Ahn | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheet.
10 | Callout | 9 | Syed Ahmed | In addition, vane pack demister shall be design to be easy for removal and install back during T&I.
11 | Text Box | 9 | JaiMun.Oh | Paint shall be performed as per BMPS-B5.
12 | Callout | 9 | Salman Jaffer | Correct numbers
13 | Text Box | 13 | Mahdi Ali | Incorrect equipment tag number. Follow the latest equipment number list issued by Owner.