## 042-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on 041C0001R shall be applied for this item. Please advised that Company does not re-write all comments for this item. Comments on this data sheet are also applicable for 043C0001R
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Sang.Hwang | Add below note
5 | Text Box | 2 | Sang.Hwang | All blank terms must be filled with verified data or marked up with "N/A" or "-" or make a note to "refer to specific mechanical drawing" unless they are not applicable. (typical comment)
6 | Callout | 2 | Saeed Taher | Change to smls
7 | Callout | 2 | Sang.Hwang | Delete this note since note (15) has been deleted
8 | Callout | 2 | balagangadhar.k | No Space (Typical for all datasheets)
9 | Text Box | 2 | balagangadhar.k | Specified FV at Design Pressure in P&ID and also refer to BMPS-A3
10 | Callout | 3 | Sang.Hwang | delete this standard
11 | Text Box | 3 | Sang.Hwang | In case there is any conflict between FEED document and Licensor's document, Contractor has to clarify and confirm with Licensor. In the Licensor's data sheet, there is a note for MH3/MH4 mentioning "Allow access to manways for catalyst dumping / removal. Manways to be positioned below center of reactor". Please re-check this point and correct.
12 | Callout | 3 | balagangadhar.k | No. (Typical for all datasheets)
13 | Callout | 3 | BD Mori | Refer note 14 on page 4 on addition of 150 mm of ½” diameter ceramic balls on top of the catalyst bed. Therefore, check and confirm with Licensor, is 6” height of 2” (50 mm) refractory lining is from top of the catalyst bed or from the top of the ceramic balls?
14 | Text Box | 3 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
15 | Callout | 3 | BD Mori | The thermocouples installed in the catalyst bed shall read the temperatures at 75%, 50% and 25% from the top of the catalysts bed. However, as per the dimensions provided in this note, the thermocouples located from top of the catalyst bed at 150 mm, 510 mm and 850 mm will read temperature at 85%, 50% and 17% from the top of the catalyst bed. Consult Licensor and make correction as required for providing the temperature reading at 75%, 50% and 25% from the catalyst bed top.
16 | Callout | 3 | BD Mori | This is already covered in the statement above this line. Therefore, check and if not required delete.
17 | Callout | 4 | Salman Jaffer | Add heading for this table
18 | Callout | 4 | Sang.Hwang | Contractor to specify it clearly
19 | Text Box | 4 | Sang.Hwang | for the proposed catalyst supplier table
20 | Callout | 4 | Sang.Hwang | Hardness value shall be re-checked as per applicable specifications and corrected
21 | Callout | 4 | Sang.Hwang | Is it necessary to indicate like this way? Please check and delete it.
22 | Text Box | 4 | Sang.Hwang | The external surface shall be coated as per BMPS-B5.
23 | Callout | 4 | Sang.Hwang | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheets.
24 | Callout | 4 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
25 | Callout | 4 | Sang.Hwang | w/impingement baffle
26 | Callout | 5 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)