## 042-G-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | . The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
2 | Text Box | 1 | balagangadhar.k | Comments provided on this datasheet are also applicable to 041P0001A/B & 043P0001A/B
3 | Text Box | 1 | Nalini Mohan | For additional comments refer to IPMT response on transmittal BMP-SOC-TRI-00087
4 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
5 | Callout | 2 | balagangadhar.k | Check pump discharge/differential pressure. As per BOD, BL pressure is 100 psig. Discharge pressure may not be adequate considering the frictional losses, static losses and control valve pressure drop.
6 | Text Box | 2 | balagangadhar.k | Fill the data
7 | Callout | 2 | balagangadhar.k | specify here and remove note 7
8 | Callout | 3 | Isamu | Since first page and note 25 indicated manufacturer's standard .. line 3 shall read " Equivalent to API pump type VS4
9 | Callout | 3 | balagangadhar.k | update if pump discharge pressure is changed
10 | Callout | 3 | balagangadhar.k | Use "CS". Remove dot.
11 | Callout | 8 | Salman Jaffer | New numbering
12 | Callout | 8 | balagangadhar.k | No.
13 | Callout | 8 | BD Mori | TTSJV shall provide the physical properties not the pump vendor. The pump vendor to design the pump for the given physical properties.