## 043-E-DAT-00002-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
2 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC Contractor shall coordinate with JV Directorate.
3 | Text Box | 1 | Sang.Hwang | All comments shown on 041E0002 shall be applied for this item. Please be advised that Company does not re-write all comments for this item.
4 | Callout | 2 | Sang.Hwang | TEMA type to be re-confirmed by the Licensor
5 | Callout | 2 | Sang.Hwang | Contractor to confirm if over design margin is included or not and its condition should be noted. (typical comment) Over design margin to be re-confirmed by the Licensor.
6 | Callout | 3 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
7 | Callout | 4 | Saeed Taher | Specify ASTM specifiaction & grade
8 | Callout | 4 | Saeed Taher | Add 'SA285GRC'
9 | Callout | 4 | Saeed Taher | Add 'CS'
10 | Callout | 4 | Saeed Taher | Add 'CS + Refractory Lined (Note 1,28)'
11 | Callout | 4 | Saeed Taher | Add 'Note 1)'
12 | Callout | 4 | Saeed Taher | Add 'Refractory Lined'
13 | Callout | 5 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
14 | Callout | 6 | Jong.Ahn | See note 35
15 | Text Box | 6 | Salman Jaffer | STUB
16 | Text Box | 6 | Salman Jaffer | WELD
17 | Text Box | 6 | Salman Jaffer | STUB
18 | Text Box | 6 | Salman Jaffer | WELD
19 | Text Box | 9 | Jong.Ahn | 35. The instrument connection size and ratings shall be complied with the section 8.1 process connection in BMPS-J2.
20 | Text Box | 9 | Mahdi Ali | Indicate the complete document number
21 | Text Box | 9 | JaiMun.Oh | Paint shall be performed as per BMPS-B5.
22 | Text Box | 9 | Syed Ahmed | In addition, vane pack demister shall be design to be easy for removal and install back during T&I.
23 | Callout | 9 | Saeed Taher | FEED data sheet & MSD indicates that hardness is limited to 237 HB. Please confirm
24 | Callout | 9 | balagangadhar.k | No. (Typical for all datasheets)
25 | Text Box | 10 | Mahdi Ali | Incorrect equipment number
26 | Text Box | 13 | Mahdi Ali | Incorrect equipment number