## 043-G-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | . The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
2 | Text Box | 1 | Nalini Mohan | For additional comments refer to IPMT response on transmittal BMP-SOC-TRI-00087, 88
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 3 | Isamu | Since first page and note 25 indicated manufacturer's standard .. line 3 shall read " Equivalent to API pump type VS4
5 | Callout | 8 | Salman Jaffer | New numbering
6 | Callout | 8 | BD Mori | TTSJV shall provide the physical properties not the pump vendor. The pump vendor to design the pump for the given physical properties.