## 044-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
2 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | Sang.Hwang | All comments shown on this item shall be applied for 45C0001R.
4 | Text Box | 2 | balagangadhar.k | Specified FV at Design Pressure in P&ID and also refer to BMPS-A3
5 | Callout | 2 | Saeed Taher | Add Note 16
6 | Callout | 2 | balagangadhar.k | No Space
7 | Callout | 2 | Sang.Hwang | Note (15) is not related this part. Please correct.
8 | Callout | 2 | Saeed Taher | Change to (smls)
9 | Text Box | 2 | Sang.Hwang | All blank terms must be filled with verified data or marked up with "N/A" or "-" or make a note to "refer to specific mechanical drawing" unless they are not applicable. (typical comment)
10 | Callout | 3 | Sang.Hwang | Please re-check insulation thickness as per BMPS-N1
11 | Callout | 3 | balagangadhar.k | This is applicable to M3 & M4 manways, also include process gas outlet nozzles.
12 | Callout | 3 | Sang.Hwang | Conflicts with note 16. Re-check and correct
13 | Text Box | 3 | Sang.Hwang | Contractor to add a typical note as "All thickness and weight terms shown in this data sheet shall be verified by strength calculations".
14 | Text Box | 3 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
15 | Callout | 3 | BD Mori | Refer note 8 on 150 mm of ½” diameter ceramic balls on top of the catalyst bed. Therefore, check and confirm with Licensor, is 150 mm height of 50 mm thick refractory lining is from top of the catalyst bed or from the top of the ceramic balls?
16 | Callout | 4 | balagangadhar.k | No.
17 | Callout | 4 | Sang.Hwang | Add heading for the proposed catalyst supplier table
18 | Callout | 4 | balagangadhar.k | (4TGTU)
19 | Callout | 4 | Sang.Hwang | w/impingement baffle
20 | Callout | 4 | Sang.Hwang | Hardness value shall be re-checked as per applicable specifications and corrected
21 | Callout | 4 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
22 | Callout | 4 | Salman Jaffer | Please refer to Bid Query T1803 and add note regarding Turndown ratio of 10%.
23 | Callout | 4 | Sang.Hwang | The instrument connection size and ratings shall be complied with the section 8.2 Process Connection of BMPS-J2. This comment is in general for all data sheet.
24 | Callout | 5 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
25 | Cloud+ | 9 | BD Mori | Add a note stating that these catalysts are not used. The catalysts specified on page 4 of the data sheet will be used in the reactor.