## 044-E-DAT-00007-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
2 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC Contractor shall coordinate with JV Directorate.
3 | Text Box | 1 | Dowon Pyun | Owner's comments in this data sheet shall be typically considered and applied in another identical exchanger 045E0002, whatever applicable.
4 | Cloud+ | 2 | BD Mori | Provide the missing information
5 | Pen | 2 | BD Mori | .
6 | Text Box | 2 | Dowon Pyun | (Typ. comment)
7 | Callout | 2 | Sang.Hwang | Over design margin to be re-confirmed by the Licensor
8 | Callout | 2 | Dowon Pyun | Fill-up
9 | Callout | 2 | Sang.Hwang | In addition, TEMA type to be re-confirmed by the Licensor
10 | Callout | 2 | Syed Ahmed | Change LP steam to 50# like other units 41,42 and 43 exchanger data sheets.
11 | Text Box | 2 | Dowon Pyun | When data terms are not applicable, they shall be shown as 'N/A' or '-'. (Typ. comment)
12 | Callout | 2 | Dowon Pyun | Contractor to confirm if over design margin is included or not and its condition should be noted (Typ. comment)
13 | Callout | 2 | Dowon Pyun | Relevant PFD shows as 'NEN'
14 | Callout | 3 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
15 | Callout | 4 | Saeed Taher | Specify ASTM specification & grade
16 | Callout | 4 | Saeed Taher | Add 'CS'
17 | Callout | 4 | Sang.Hwang | Is lining required? There is no mention on the Licensor's data sheet. Please re-check & correct it.
18 | Callout | 4 | Saeed Taher | Add "CS (Note 11)'
19 | Callout | 5 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
20 | Callout | 6 | Sang.Hwang | description to be reversed each other
21 | Callout | 6 | Jong.Ahn | The instrument connection size and ratings shall be complied with the section 8.1 Process connection in BMPS-J2. This comment is in general for all data sheet.
22 | Callout | 9 | balagangadhar.k | No.
23 | Callout | 9 | balagangadhar.k | Check Note 18, duplication of notes
24 | Callout | 9 | Saeed Taher | FEED datasheet & MSD indicate that hardness is limited to 237 HB. Please confirm
25 | Text Box | 9 | JaiMun.Oh | Paint shall be performed as per BMPS-B5.
26 | Callout | 9 | balagangadhar.k | Unit