## 045-C-DAT-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 2 | balagangadhar.k | Specified FV at Design Pressure in P&ID and also refer to BMPS-A3
2 | Callout | 2 | balagangadhar.k | No Space
3 | Callout | 4 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
4 | Callout | 4 | balagangadhar.k | No.
5 | Callout | 4 | balagangadhar.k | (3TGTU)
6 | Callout | 5 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
7 | Callout | 3 | BD Mori | Refer note 8 on 150 mm of ½” diameter ceramic balls on top of the catalyst bed. Therefore, check and confirm with Licensor, is 150 mm height of 50 mm thick refractory lining is from top of the catalyst bed or from the top of the ceramic balls?
8 | Cloud+ | 9 | BD Mori | Add a note stating that these catalysts are not used. The catalysts specified on page 4 of the data sheet will be used in the reactor.
9 | Text Box | 3 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
10 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
11 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
12 | Callout | 2 | Saeed Taher | Add Note 16
13 | Callout | 2 | Saeed Taher | Change to (smls)
14 | Callout | 4 | Salman Jaffer | Please refer to Bid Query T1803 and add note regarding Turndown ratio of 10%.
15 | Text Box | 1 | Sang.Hwang | All comments shown on 044C0001R shall be applied for this item.
16 | Callout | 3 | Sang.Hwang | Delete this standard
17 | Callout | 3 | Sang.Hwang | Conflicts with note 16. Please re-check and correct
18 | Callout | 3 | Sang.Hwang | Insulation thickness to be re-checked as per BMPS-N1
19 | Callout | 4 | Sang.Hwang | Add heading for the proposed catalyst supplier table
20 | Callout | 4 | Sang.Hwang | The instrument connection size and ratings shall be complied with section 8.2 Process Connection in BMPS-J2. This comment is in general for all data sheet.
21 | Callout | 4 | Sang.Hwang | w/impingement baffle
22 | Callout | 4 | Sang.Hwang | Hardness value shall be re-checked as per applicable specifications and corrected