## 045-E-DAT-00004-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
2 | Text Box | 1 | Sang.Hwang | All comments shown on 044E0002 shall be applied for this item. Please be advised that Company does not re-write all comments for this item.
3 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. SOC Contractor shall coordinate with JV Directorate.
4 | Cloud+ | 2 | BD Mori | provide the missing information
5 | Callout | 2 | balagangadhar.k | 60#
6 | Callout | 3 | Jeung.Kim | Contractor or Vendor has to verify the thermal rating- typical comment
7 | Callout | 3 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
8 | Callout | 4 | Saeed Taher | Specify ASTM specification & grade
9 | Callout | 4 | Saeed Taher | Add 'CS'
10 | Callout | 4 | Sang.Hwang | Please re-check and correct it.
11 | Callout | 4 | Saeed Taher | Add 'CS (Note 11)'
12 | Callout | 5 | balagangadhar.k | Change this to "Note A" or "Note I", to avoid confusion, typical for all datasheets
13 | Callout | 6 | Jong.Ahn | The instrument connection size and ratings shall be complied with the section 8.1 Process connection in BMPS-J2. This comment is in general for all equipment data sheet.
14 | Callout | 9 | Saeed Taher | FEED datasheet & MSD indicate that hardness is limited to 237 HB. Please confirm
15 | Callout | 9 | balagangadhar.k | Check Note 18, duplication of notes
16 | Callout | 9 | balagangadhar.k | No.
17 | Callout | 9 | balagangadhar.k | Unit
18 | Text Box | 9 | JaiMun.Oh | Paint shall be performed as per BMPS-B5.