## 048-A-MSD-00001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | 2
2 | Text Box | 1 | Mahdi Ali | 3
3 | Text Box | 1 | Mahdi Ali | 4
4 | Text Box | 1 | Mahdi Ali | 5
5 | Text Box | 1 | Mahdi Ali | 6
6 | Text Box | 1 | Mahdi Ali | 7
7 | Text Box | 1 | Nalini Mohan | As a special case, this transmittal is issued under Code 2 in order to facilitate subsequent engineering development. As agreed resubmit the document deleting the VE item.
8 | Text Box | 1 | Mahdi Ali | General Notes: 1. Use the latest border that is part of the homogenization procedure. 2. Scale: NTS 3. Size: A1 4. TTL SHTS: 001 5. Where is sheets 1 and 2? 6. Remove the abbreviation in the Unit field 7. Remove '#' from the units short format
9 | Callout | 1 | Saeed Taher | HIC resistant plates required as per datasheet
10 | Callout | 1 | Saeed Taher | HIC resistant plates required as per datasheet, refer to Bid Query T1636
11 | Callout | 1 | Saeed Taher | Pump class to be changed to D1, refer to Bid Query T1633
12 | Callout | 1 | Saeed Taher | PWHT is required for all CS welds including tube to tube sheet strength welding joints
13 | Text Box | 1 | BD Mori | This MSD contains some of the equipment which are not as per FEED PFD. Some of the equipment added in this MSD as a value engineering, which was not accepted by Bapco. Therefore, resubmit the MSD which is in line with the original FEED PFD with EPC input included in it for review .