## 085-A-PID-00011-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | According to the H&MB and design basis, 10% of the "total CW make flow rate" is routed through the calcite beds. However, stream "B" does not represent the total make flowrate (total less the amount routed to the calcite beds) and hence A/B ratio will not be 10% (higher than 10%). TR to check and amend as necessary. Also rephrase the note for clarity. review the viability of relocating the F0005 to stream 1 to give direct measurement of the total Make-up flow and direct control of the flow ratio.
2 | Text Box | 1 | A.Jabbar Mahmood | Add a note to clarify the function of each of the XVs
3 | Call-out | 1 | 986131 | Equipment number and Line numbers to be provided.
4 | Call-out | 1 | 986131 | Fill in all other relevant details.
5 | Cloud+ | 1 | A.Jabbar Mahmood | Shall read as "MAIN CW MAKE-UP TO MAIN COOLING WATER BASIN BA0001
6 | Call-out | 1 | 986131 | The drain can be acidic water and must first be taken to a sump with facility to neutralize before discharging to CSS. This comments applies to all the drain from the calcite bed package. Please correct as required.