## 098-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | All comments shown on this item shall be applied for 099C0001R.
2 | Call-out | 1 | Hasan Al Noaimi | No.3 Hydrogen Plant
3 | Call-out | 1 | MAK | Or 3H2 Plant
4 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
5 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
6 | Callout | 2 | Sang.Hwang | All plates shall be normalized condition
7 | Callout | 2 | Sang.Hwang | Delete "-" for external pressure
8 | Callout | 2 | BD Mori | General comment 1) How external pressure is negative? 2) If it is full vacuum specify, 14.7 psig external pressure. 3) If it is half vacuum specify,10 psig external pressure 4) Steamout conditions are not specified in this data sheet, check and provide feedback.
9 | Call-out | 2 | Syed Ahmed | No.3 Hydrogen Plant
10 | Callout | 2 | Sang.Hwang | Note (6) and indicate SS304 are not matched. Please re-check and correct
11 | Cloud+ | 2 | BD Mori | Provide this data.
12 | Callout | 2 | Sang.Hwang | smls
13 | Callout | 2 | Sang.Hwang | Typical for 098C0002R/098C0003R and also for unit 099
14 | Callout | 3 | Sang.Hwang | Contractor to confirm and delete this note
15 | Callout | 3 | Sang.Hwang | Delete this standard
16 | Text Box | 3 | Sang.Hwang | Hot box shall be provided on skirt.
17 | Callout | 3 | BD Mori | Modify the note based on the information provided in the sketch below, including the type and opening in the Johnson screen for more clarity.
18 | Callout | 3 | BD Mori | Reword this note: Catalyst selection will be done later
19 | Text Box | 3 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
20 | Callout | 3 | BD Mori | The specification for Inert balls appears to be incorrect. Check with Licensor and correct as required.
21 | Text Box | 4 | Syed Ahmed | General comment: please mention both units (meter and feet) as the PFD dimension using both units.
22 | Callout | 4 | BD Mori | More detail information required. Consult licensor
23 | Text Box | 4 | Syed Ahmed | Please specify/mention the dimension from the ( N6 )dump nozzle end point to the ground.
24 | Callout | 4 | Syed Ahmed | This should be drain not vent, please check with vendor, if yes, change the direction to the down side and update the nozzle schedule table below
25 | Callout | 4 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
26 | Callout | 4 | Salman Jaffer | With reference to Bid Query T1346, please add this note (The height shown in this datasheet is estimated and can vary basis requirement from selected catalyst vendor).
27 | Callout | 5 | Sang.Hwang | Change it as "drain"
28 | Callout | 5 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)