## 098-C-DAT-00003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | BD Mori | Comments on this data sheet are also applicable to 099C0003R
2 | Call-out | 1 | Hasan Al Noaimi | No.3 Hydrogen Plant
3 | Call-out | 1 | MAK | Or 3H2 Plant
4 | Text Box | 1 | Nalini Mohan | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details (including Licensor clarifications) and be in code 2 approval status.
5 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
6 | Callout | 2 | BD Mori | During the fresh catalyst start-up Bapco experienced HTS outlet temperature up 956 °F due to the catalyst heat of hydration in 2011. Other plants have experienced this temperature as high as 1110°F. Therefore, consult licensor to review the HTS outlet design temperature and provide justification for selection of 850°F design temperature.
7 | Callout | 2 | BD Mori | General comment 1) How external pressure is negative? 2) If it is full vacuum specify, 14.7 psig external pressure. 3)If it is half vacuum specify,10 psig external pressure 4)4) Steamout conditions are not specified in this data sheet, check and provide feedback.
8 | Cloud+ | 2 | BD Mori | It appears that values are -ve. Correct them to remove -ve sign. Also refer P&ID and add note that start of run (SOR) temperature is 630°F.
9 | Callout | 3 | BD Mori | Add note note based on the information provided in the sketch below, including the type and opening in the Johnson screen for more clarity.
10 | Callout | 3 | Sang.Hwang | C3
11 | Text Box | 3 | JaiMun.Oh | Flanges shall be in accordance with ASME B16.47 series-B for NPS 26 and larger.
12 | Callout | 3 | BD Mori | High purity alumina inert balls not exceeding 0.20 wt% SiO2. Consult licensor for the specification
13 | Text Box | 3 | Syed Ahmed | Please add note regarding the MPT (Minimum Pressurizing Temp) to specify the temperature and pressure.
14 | Text Box | 3 | JaiMun.Oh | The external surface shall be coated as per BMPS-B5.
15 | Callout | 4 | Sang.Hwang | Contractor to specify the detail design of skirt to shell attachment requirement as per para. 4.1.3 of BMPS-A25. And also, add a note for "hot box".
16 | Callout | 4 | Sang.Hwang | Contractor to verify it with the latest P & ID
17 | Text Box | 4 | Syed Ahmed | General comment: please mention both units (meter and feet) as the PFD dimension using both units.
18 | Callout | 4 | BD Mori | More detail information required. Consult licensor
19 | Text Box | 4 | Syed Ahmed | N7
20 | Callout | 4 | Syed Ahmed | ONE drain point is very essential for operation during hot steam standby mode to remove any condensate from the HT shift reactor, please check with vendor, if yes, please update the nozzle schedule table below
21 | Text Box | 4 | Syed Ahmed | Please specify/mention the dimension from the ( N6 )dump nozzle end point to the ground.
22 | Callout | 4 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
23 | Callout | 4 | Salman Jaffer | With reference to Bid Query T1346, please add this note (The height shown in this datasheet is estimated and can vary basis requirement from selected catalyst vendor).
24 | Callout | 5 | balagangadhar.k | Use M/H for Manway (typical for all datasheets)
25 | Text Box | 5 | Salman Jaffer | What is the retinal for deletion of sheet 5 of 6 of FEED data sheets (SKIRT, WEIGHTS & LOADING DATA) from this document?